AI-POWERED EMAIL SORTER Task Implementation Guide IMPL-EMAILSORT-001 · v1.0 · 2026-03-10 7 Phases · 40 Tasks · 15 Weeks

# How to Use This Document

This document is a phase-by-phase implementation guide for the AI-Powered Email Sorter project. It is intended to be used alongside the Technical Specification (SPEC-EMAILSORT-001) and Project Plan (PROJ-EMAILSORT-001).

Each phase section opens with a description of its purpose and scope, followed by a task summary table. Each task then begins on a new page and contains four elements:

| Element | Description | How to Use |
| --- | --- | --- |
| Modules | Files created or modified by the task | Use as a checklist to verify all files are addressed |
| APIs | External services and SDK methods called | Reference during implementation to confirm correct API usage |
| Data | Firestore fields, secrets, and state created, read, or changed | Verify data model compliance with SPEC-EMAILSORT-001 Section 5 |
| AI Prompt | A complete, self-contained prompt for an AI coding assistant | Copy the prompt verbatim when directing an AI to implement the task |

Important: The AI implementation prompts are designed to be used with Claude Sonnet or equivalent. Each prompt is self-contained. However, always provide the AI assistant with the relevant existing source files as context before submitting the prompt. Review all AI-generated code before committing. The prompts specify behaviour; the AI may choose implementation approaches that require adjustment.

PHASE 1 Foundation Weeks 1–2 · 7 Tasks

Phase 1 establishes every structural element the project depends on. No application features are built here — instead, this phase creates the conditions under which all subsequent phases can proceed safely and repeatably.

The phase covers four areas. First, the GitHub repository is initialised with a branch strategy, CI/CD stub, and all configuration files. Second, the Firebase project is created on the Blaze plan with a $0 spend cap, and all required services — Firestore, Authentication, and Cloud Functions — are enabled and configured. Third, Google OAuth 2.0 is wired through Firebase Auth so that a user can sign in and receive a verified session token. Fourth, a minimal React application is scaffolded, connected to Firebase, and deployed to GitHub Pages so that end-to-end deployment is proven before any business logic is written.

Phase 1 is complete when a user can open the deployed URL, sign in with their Google account, see an authenticated shell, and sign out — with the full CI/CD pipeline triggering automatically on every push to main.

## Task Summary

| Task ID | Week | Task Name |
| --- | --- | --- |
| 1.1 | Week 1 | GitHub Repository + Branch Strategy |
| 1.2 | Week 1 | GitHub Actions CI/CD Pipeline |
| 1.3 | Week 1 | Firebase Project Setup (Blaze + $0 Cap) |
| 1.4 | Week 1 | Firebase Auth + Google OAuth |
| 1.5 | Week 2 | React App Skeleton + Routing |
| 1.6 | Week 2 | Firestore Rules + Indexes |
| 1.7 | Week 2 | Deploy Authenticated Shell to GitHub Pages |

Task 1.1 — GitHub Repository + Branch Strategy Phase 1 · Week 1 · 1.1

Description

Create the GitHub repository, establish the branch strategy, commit all configuration scaffold files, and verify the remote is accessible.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| email-sorter/ | Root repository directory |
| .gitignore | Excludes node_modules, .env files, build outputs, OS artefacts |
| README.md | Project overview, setup instructions, secrets table, cost profile |
| BRANCH-STRATEGY.md | Formal record of main-only strategy with future migration path |
| .github/CODEOWNERS | Single-owner declaration |
| .github/workflows/deploy.yml | CI/CD pipeline stub — completed in Task 1.2 |
| .vscode/extensions.json | Recommended VS Code extensions |
| .vscode/settings.json | Format on save, tab size, rulers |
| firebase.json | Firebase project configuration — Firestore, Functions, Emulators |
| firestore.rules | Security rules stub — completed in Task 1.6 |
| firestore.indexes.json | All 6 composite index definitions from the Specification |
| frontend/.env.example | Frontend environment variable template |
| functions/.env.example | Functions environment variable template |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a senior software engineer starting a new project called 'AI-Powered Email Sorter'. The technology stack is: React.js frontend hosted on GitHub Pages, Node.js Firebase Cloud Functions backend, Firestore database, Firebase Auth with Google OAuth, Anthropic Claude API for email classification, Gmail API, Microsoft Graph API, and IMAP/SMTP for email ingestion. Task: Initialise the GitHub repository scaffold. Create the following files with production-quality content: 1. README.md — project title, tech stack table, repo structure tree, branch strategy, local dev setup steps (prerequisites, clone, npm install, env vars, emulators, dev server), GitHub Secrets table (FIREBASE_TOKEN, REACT_APP_FIREBASE_*, ANTHROPIC_API_KEY, ENCRYPTION_SECRET), deployment instructions, and cost profile table. 2. .gitignore — cover node_modules, build/, .env variants, .firebase/, .vscode/* (except extensions.json and settings.json), OS artefacts (.DS_Store, Thumbs.db), logs. 3. BRANCH-STRATEGY.md — document main-only strategy with rationale, branch protection rules table, commit message convention (feat/fix/chore/docs/test/refactor/ci), and future feature-branch migration guide. 4. .github/CODEOWNERS — single owner, all files. 5. .vscode/extensions.json — recommend: prettier, eslint, firebase explorer, gitlens, material-icon-theme, es7-react-snippets. 6. .vscode/settings.json — formatOnSave: true, tabSize: 2, rulers: [100], trimTrailingWhitespace, insertFinalNewline. 7. firebase.json — configure firestore (rules + indexes), functions (source: functions, Node.js), emulators (auth:9099, firestore:8080, functions:5001, ui:4000). 8. firestore.rules — stub that allows authenticated users to read/write only their own users/{uid} document and all sub-collections. Deny all else. 9. firestore.indexes.json — define composite indexes for: emails(folder+receivedAt), emails(folder+confidence), emails(isTrainingExample+folder), emails(syncedAt), rules(priority+enabled), training(folder+createdAt). 10. frontend/.env.example — all REACT_APP_ vars with comments. 11. functions/.env.example — ANTHROPIC_API_KEY, ENCRYPTION_SECRET, FIREBASE_PROJECT_ID. After creating files, initialise git, make initial commit with message: 'feat: task 1.1 — repo scaffold and branch strategy' Set remote to https://github.com/{USERNAME}/email-sorter.git and push to main.

Task 1.2 — GitHub Actions CI/CD Pipeline Phase 1 · Week 1 · 1.2

Description

Replace the deploy.yml stub with a complete two-job GitHub Actions pipeline that installs dependencies, runs tests, builds the React app with injected secrets, deploys Cloud Functions, and publishes the frontend to GitHub Pages.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| .github/workflows/deploy.yml | Complete CI/CD pipeline — replaces stub from Task 1.1 |

APIs Used

| API / Service | Usage |
| --- | --- |
| GitHub Actions | ubuntu-latest runner, actions/checkout@v4, actions/setup-node@v4, actions/deploy-pages@v4 |
| Firebase CLI | firebase deploy --only functions,firestore:rules via FIREBASE_TOKEN secret |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| GitHub Secret: FIREBASE_TOKEN | Firebase CI token for headless deployment |
| GitHub Secret: REACT_APP_FIREBASE_* | Firebase config injected at React build time |
| GitHub Secret: ANTHROPIC_API_KEY | Injected into Functions environment — never into frontend |
| GitHub Secret: ENCRYPTION_SECRET | AES-256 key for IMAP credential encryption |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a senior DevOps engineer. Create a complete GitHub Actions CI/CD pipeline for the AI-Powered Email Sorter project. File: .github/workflows/deploy.yml Trigger: push to main branch only. Job 1 — test-and-build (runs on ubuntu-latest): Steps: 1. actions/checkout@v4 2. actions/setup-node@v4 with node-version: '20' 3. Cache npm dependencies for both frontend/ and functions/ directories 4. cd frontend && npm ci 5. cd frontend && npm test -- --watchAll=false --passWithNoTests 6. cd frontend && npm run build env: inject all REACT_APP_* secrets from GitHub Secrets using ${{ secrets.NAME }} REACT_APP_USE_EMULATORS must be set to 'false' for production builds 7. cd functions && npm ci 8. Upload frontend/build as a GitHub Pages artifact using actions/upload-pages-artifact@v3 Job 2 — deploy (depends on: test-and-build): permissions: pages: write, id-token: write Steps: 1. actions/checkout@v4 2. actions/setup-node@v4 with node-version: '20' 3. cd functions && npm ci 4. Install Firebase CLI: npm install -g firebase-tools 5. firebase deploy --only functions,firestore:rules,firestore:indexes env: FIREBASE_TOKEN: ${{ secrets.FIREBASE_TOKEN }} ANTHROPIC_API_KEY: ${{ secrets.ANTHROPIC_API_KEY }} ENCRYPTION_SECRET: ${{ secrets.ENCRYPTION_SECRET }} 6. actions/deploy-pages@v4 to publish the uploaded artifact to GitHub Pages Requirements: - ANTHROPIC_API_KEY must ONLY appear in the deploy job environment, never in test-and-build - Use concurrency group to cancel in-progress runs on new push - Add clear step names for readable pipeline logs - Pipeline must complete in under 5 minutes on a clean run

Task 1.3 — Firebase Project Setup (Blaze + $0 Cap) Phase 1 · Week 1 · 1.3

Description

Create the Firebase project, upgrade to Blaze plan, configure a $0 spend cap, enable all required services, and generate the service account credentials needed for local development.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| firebase.json | Already exists — verify project ID matches created project |
| .firebaserc | Created by firebase use — links local project to Firebase project ID |
| functions/src/index.js | Initial Cloud Functions entry point — exports empty object |
| functions/package.json | Functions dependencies — firebase-admin, firebase-functions, node 20 |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Console | Project creation, Blaze upgrade, spend cap, service enablement |
| Firebase CLI | firebase login, firebase use --add, firebase init |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Firebase Project ID | Stored in .firebaserc and all .env files |
| Firebase API Key | Added to GitHub Secrets as REACT_APP_FIREBASE_API_KEY |
| Firebase Auth Domain | Added to GitHub Secrets as REACT_APP_FIREBASE_AUTH_DOMAIN |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Firebase architect. Provide complete step-by-step instructions to set up a Firebase project for the AI-Powered Email Sorter application. Cover the following in order: 1. FIREBASE CONSOLE SETUP: - Create a new Firebase project named 'email-sorter' (or 'email-sorter-prod') - Upgrade to Blaze (pay-as-you-go) plan - Configure a $0 budget alert: Console > Project Settings > Usage and Billing. Set budget amount to $0.01 USD, enable email alerts at 50% and 100% thresholds. Explain that Firebase does not offer a hard spend cap UI — the $0 cap is enforced by setting Cloud Functions to have no outbound traffic quota override, and by monitoring the budget alert immediately. - Enable Firestore: Build > Firestore Database > Create database > Production mode > choose region (us-central1 recommended for lowest latency with Cloud Functions) - Enable Firebase Auth: Build > Authentication > Get started > Sign-in method > Google > Enable - Enable Cloud Functions: Build > Functions > Get started 2. FIREBASE CLI SETUP: - firebase login (opens browser OAuth flow) - firebase use --add (select the project just created, alias: default) - Verify .firebaserc is created with correct project ID 3. FUNCTIONS INITIALISATION: Create functions/package.json with dependencies: firebase-admin: ^12.0.0, firebase-functions: ^5.0.0 devDependencies: eslint engines: node 20 main: src/index.js Create functions/src/index.js as a minimal stub: const functions = require('firebase-functions'); // Cloud Functions implemented in Tasks 2.2 onwards exports.placeholder = functions.https.onRequest((req, res) => res.send('OK')); 4. ENVIRONMENT SECRETS: - firebase functions:secrets:set ANTHROPIC_API_KEY - firebase functions:secrets:set ENCRYPTION_SECRET (generate with: node -e "console.log(require('crypto').randomBytes(32).toString('hex').slice(0,32))") 5. GITHUB SECRETS: List every value from Firebase Console > Project Settings > Your apps that must be added to GitHub repository secrets, with exact secret names matching .env.example. 6. VERIFICATION: - firebase deploy --only functions - Confirm placeholder function appears in Firebase Console > Functions - Confirm Firestore database is visible in Console > Firestore

Task 1.4 — Firebase Auth + Google OAuth Phase 1 · Week 1 · 1.4

Description

Configure Google OAuth 2.0 credentials in Google Cloud Console, wire Firebase Auth in the React app, and implement the sign-in and sign-out flow with session persistence.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/context/AuthContext.jsx | Firebase Auth state provider — exposes user, loading, signIn, signOut |
| frontend/src/components/LoginPage.jsx | Sign-in page with Google OAuth button |
| frontend/src/components/GoogleSignInButton.jsx | Styled OAuth button component |
| frontend/src/firebase.js | Firebase app initialisation — reads REACT_APP_FIREBASE_* env vars |
| frontend/src/App.jsx | Root component — renders LoginPage if unauthenticated, MainLayout if authenticated |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Auth SDK | signInWithPopup(auth, googleProvider), signOut(auth), onAuthStateChanged(auth, cb) |
| GoogleAuthProvider | new GoogleAuthProvider() — requests profile and email scopes |
| Firebase Admin SDK | admin.auth().verifyIdToken(token) — used in all Cloud Functions to verify caller |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid} | Document created on first sign-in: uid, email, displayName, createdAt |
| Firebase ID Token | JWT stored in memory — attached as Authorization: Bearer {token} on all function calls |
| Session persistence | browserLocalPersistence — survives page reload, cleared on signOut |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React and Firebase authentication engineer. Implement Google OAuth sign-in for the AI-Powered Email Sorter React application. Stack: React 18, Firebase SDK v10+, functional components, React hooks. 1. frontend/src/firebase.js: Import initializeApp, getAuth, getFirestore from firebase SDK. Read all config from process.env.REACT_APP_FIREBASE_* variables. If process.env.REACT_APP_USE_EMULATORS === 'true', connect to emulators: connectAuthEmulator(auth, 'http://localhost:9099') connectFirestoreEmulator(db, 'localhost', 8080) Export: app, auth, db. 2. frontend/src/context/AuthContext.jsx: Create AuthContext with createContext. AuthProvider component: - State: user (null initially), loading (true initially) - useEffect: subscribe to onAuthStateChanged. On user sign-in, create/update Firestore document at users/{uid} with setDoc(merge:true): { uid, email, displayName, lastLoginAt: serverTimestamp() } On first creation only, also set createdAt: serverTimestamp(). - signIn(): call signInWithPopup(auth, new GoogleAuthProvider()) - signOut(): call signOut(auth) - getIdToken(): return auth.currentUser.getIdToken() - Expose: { user, loading, signIn, signOut, getIdToken } Export useAuth hook: return useContext(AuthContext) 3. frontend/src/components/LoginPage.jsx: Full-page centred layout. Dark navy background matching project palette (#0A1628). Show: project title 'AI-Powered Email Sorter', subtitle, Google sign-in button. Show loading spinner while auth state is initialising. Show error message if signIn() throws. 4. frontend/src/App.jsx: Wrap entire app in AuthProvider. If loading: show full-page spinner. If user is null: render LoginPage. If user exists: render MainLayout (stub — just show 'Authenticated as {email}' for now). 5. functions/src/auth/verifyToken.js: Export middleware function verifyToken(context) that: - Checks context.auth exists (Firebase callable functions populate this automatically) - Throws functions.https.HttpsError('unauthenticated', 'Authentication required') if not - Returns context.auth.uid All subsequent Cloud Functions must call verifyToken(context) as their first line. Error handling: catch signIn errors, display 'Sign-in failed. Please try again.' to user. Never log tokens or user credentials to the console.

Task 1.5 — React App Skeleton + Routing Phase 1 · Week 2 · 1.5

Description

Build the full application shell — top bar, sidebar with folder list, email list panel, and email detail panel — as empty but correctly structured components. Establish React Router for navigation between views.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/App.jsx | Add React Router — BrowserRouter wrapping routes |
| frontend/src/components/MainLayout.jsx | Three-panel layout: sidebar, email list, email detail |
| frontend/src/components/TopBar.jsx | Header: app title, sync button (stub), account status, user menu |
| frontend/src/components/Sidebar.jsx | Folder list + account list |
| frontend/src/components/FolderList.jsx | Seven folder items with icons and unread counts (all zero for now) |
| frontend/src/components/FolderItem.jsx | Single folder row — name, count badge, active state |
| frontend/src/components/EmailListPanel.jsx | Email list for active folder — empty state for now |
| frontend/src/components/EmailDetailPanel.jsx | Email detail view — empty state for now |
| frontend/src/context/FolderContext.jsx | Active folder state — default to 'uncategorized' |
| frontend/src/index.jsx | Entry point — renders App into #root |
| frontend/public/index.html | HTML shell — sets title, meta viewport, root div |
| frontend/public/404.html | Identical to index.html — SPA routing fallback for GitHub Pages |
| frontend/package.json | React 18, react-router-dom, firebase SDK, react-scripts |

APIs Used

| API / Service | Usage |
| --- | --- |
| React Router v6 | BrowserRouter, Routes, Route, useNavigate, useParams |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| FolderContext | activeFolder (string), setActiveFolder (function) |
| Folder definitions | Static array: work, students, newsletters, receipts, personal, spam, uncategorized |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React engineer. Build the application shell for the AI-Powered Email Sorter. Use React 18, React Router v6, functional components, and CSS modules or inline styles. Do not use any UI component library — build all components from scratch. Design system (apply consistently): Background: #0A1628 (navy), #0D2137 (deep), #1A3A5C (mid) Accent: #2196F3 (blue), #00BCD4 (teal) Text: #FFFFFF (primary), #B0C4D8 (secondary), #7899AA (muted) Surface: #FFFFFF (cards), #F0F4F8 (page bg), #D0DEF0 (borders) Status: #4CAF50 (green), #FF9800 (amber), #F44336 (red) Layout (three-panel, full viewport height): Sidebar: 220px fixed width, dark navy background - App logo/title at top - FolderList: 7 folders, each with icon + name + count badge Folders: Work(💼), Students(🎓), Newsletters(📰), Receipts(🧾), Personal(👤), Spam(🚫), Uncategorized(🔬) - AccountList at bottom (empty stub for now) Email list panel: 380px width, white background - FolderActionBar at top (delete all, mark all read — disabled stubs) - Empty state: 'No emails in this folder' centred message Email detail panel: remaining width - Empty state: 'Select an email to read it' centred message TopBar (60px height, navy background, blue bottom border 3px): - Left: app icon + 'AI-Powered Email Sorter' title - Centre: SyncButton (disabled stub, shows 'Sync Email') - Right: signed-in user avatar/email + sign-out button FolderContext: Provides activeFolder (default: 'uncategorized') and setActiveFolder. Clicking a FolderItem calls setActiveFolder with the folder id. Active folder highlighted with accent colour in sidebar. Routing: / → redirect to /folder/uncategorized /folder/:folderId → show EmailListPanel for that folder /folder/:folderId/:emailId → show EmailListPanel + EmailDetailPanel 404.html: copy of index.html exactly — required for GitHub Pages SPA routing. package.json: set homepage to 'https://{USERNAME}.github.io/email-sorter' This is required for React Router to work correctly on GitHub Pages.

Task 1.6 — Firestore Rules + Indexes Phase 1 · Week 2 · 1.6

Description

Replace the firestore.rules stub with production-grade security rules, validate them with the Firebase Rules Playground, and verify all composite indexes deploy without errors.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| firestore.rules | Production security rules — replaces stub from Task 1.1 |
| firestore.indexes.json | Already complete from Task 1.1 — verify deployment succeeds |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Rules Playground | Console > Firestore > Rules > Rules Playground — test read/write scenarios |
| Firebase CLI | firebase deploy --only firestore:rules,firestore:indexes |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid} | Read/write: authenticated user where auth.uid == uid only |
| users/{uid}/{subcollection}/{docId} | Same rule inherited — all sub-collections protected |
| All other paths | Explicitly denied — allow read, write: if false |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Firebase security engineer. Write production-grade Firestore Security Rules for the AI-Powered Email Sorter application. Data model: users/{uid} — user profile document users/{uid}/accounts/{id} — connected email accounts (contains encrypted tokens) users/{uid}/emails/{id} — classified email metadata users/{uid}/rules/{id} — user-defined classification rules users/{uid}/training/{id} — training signals from user corrections users/{uid}/trainingContext — single document: cached training context string Security requirements: 1. Only authenticated users can access any data. 2. Users can only read and write their own documents (auth.uid must equal the uid path segment in every operation). 3. The accounts sub-collection contains encrypted OAuth tokens. Add a rule that PREVENTS the client from reading the accessToken and refreshToken fields directly. These fields may only be written or read by Cloud Functions (Admin SDK bypasses rules). Implement using: allow read: if !('accessToken' in resource.data) is not feasible — instead, document in comments that token fields are Admin-SDK-only and the frontend must never request these fields. Add a field mask note. 4. Deny all access to any path not explicitly matched. 5. Include helper functions to keep rules readable: isAuthenticated(), isOwner(uid). After writing the rules file: 1. Deploy: firebase deploy --only firestore:rules 2. Test in Rules Playground with these scenarios: PASS: authenticated user reads their own users/{uid} document PASS: authenticated user writes to users/{uid}/emails/{id} FAIL: unauthenticated request to any path FAIL: user A reads users/{userB_uid}/emails/{id} FAIL: any request to a path outside users/ 3. Deploy indexes: firebase deploy --only firestore:indexes 4. Confirm all 6 indexes appear as 'Enabled' in Console > Firestore > Indexes (indexes may take 2-5 minutes to build on first deployment)

Task 1.7 — Deploy Authenticated Shell to GitHub Pages Phase 1 · Week 2 · 1.7

Description

Trigger the complete CI/CD pipeline for the first time, verify the React shell deploys successfully to GitHub Pages, and confirm end-to-end authentication works on the live URL.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/package.json | Verify homepage field is set to GitHub Pages URL |
| .github/workflows/deploy.yml | Complete pipeline from Task 1.2 — triggered by push to main |
| frontend/public/404.html | Verify SPA routing fallback is present and identical to index.html |

APIs Used

| API / Service | Usage |
| --- | --- |
| GitHub Pages | Settings > Pages > Source: GitHub Actions — must be enabled before first deploy |
| GitHub Actions | Actions tab — monitor pipeline run, verify both jobs pass |
| Firebase Auth | Live Google OAuth on deployed URL — not emulator |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| GitHub Pages URL | https://{username}.github.io/email-sorter — confirm app loads |
| Firebase Auth Authorised Domain | Add GitHub Pages domain to Firebase Console > Auth > Settings > Authorised domains |
| Google OAuth Redirect URI | Add https://{username}.github.io to Google Cloud Console > OAuth consent screen > Authorised redirect URIs |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a deployment engineer. Provide a complete verified deployment checklist for deploying the AI-Powered Email Sorter React shell to GitHub Pages for the first time. Pre-deployment checklist (verify each before pushing): 1. frontend/package.json homepage field: 'https://{username}.github.io/email-sorter' 2. frontend/public/404.html exists and is identical to index.html 3. All GitHub Secrets are set: FIREBASE_TOKEN, all REACT_APP_* vars, ANTHROPIC_API_KEY, ENCRYPTION_SECRET, REACT_APP_FUNCTIONS_BASE_URL (use placeholder URL for now — real URL known after first Functions deploy) 4. GitHub Pages is enabled: repository Settings > Pages > Source > GitHub Actions 5. Firebase Auth has GitHub Pages domain in Authorised domains list 6. Google Cloud Console OAuth client has GitHub Pages URL in Authorised redirect URIs Deployment steps: 1. git add . && git commit -m 'feat: task 1.7 — deploy authenticated shell to GitHub Pages' 2. git push origin main 3. Go to GitHub > Actions tab — watch the pipeline run 4. If test-and-build job fails: describe how to read the error log and the 3 most common failure causes (missing secret, wrong homepage URL, failed npm test) 5. If deploy job fails: describe how to check Firebase CLI authentication errors Post-deployment verification: 1. Open https://{username}.github.io/email-sorter 2. Verify login page renders with Google sign-in button 3. Click sign in — Google OAuth popup should appear 4. Complete sign-in — app should show authenticated shell with user email in top bar 5. Open Firebase Console > Firestore > users collection — verify user document was created 6. Sign out — verify redirect back to login page 7. Navigate directly to https://{username}.github.io/email-sorter/folder/work Verify the page loads (not a 404) — confirms SPA routing fallback works Phase 1 is complete when all 7 verification steps pass.

PHASE 2 Gmail + AI Classification Weeks 3–5 · 6 Tasks

Phase 2 delivers the core value proposition of the application: email arrives from Gmail, the AI classifies it, and the user sees organised folders in real time. This phase is the highest-priority deliverable in the project and is the primary measure of success at the end of week 5.

The phase has two parallel tracks. The integration track connects to the Gmail API, fetches messages using the authenticated user's OAuth tokens, and writes email metadata to Firestore. The AI track sends each fetched message to the Anthropic Claude Haiku API with a carefully designed classification prompt, interprets the structured JSON response, applies confidence thresholds, and stores the result alongside the email metadata.

By the end of Phase 2, the user can trigger a sync from the UI, watch emails appear in categorised folders in real time via Firestore listeners, see a confidence score on every email, and verify that the AI is making reasonable classification decisions. The rule engine is not yet in place — that is Phase 4. All classification in this phase goes through the Claude API.

## Task Summary

| Task ID | Week | Task Name |
| --- | --- | --- |
| 2.1 | Week 3 | Gmail API Integration (Fetch/List) |
| 2.2 | Week 3 | Cloud Function: syncEmails |
| 2.3 | Week 4 | Claude Haiku Classifier |
| 2.4 | Week 4 | Confidence Scoring + Thresholds |
| 2.5 | Week 4 | React Folder View + Email List UI |
| 2.6 | Week 5 | Firestore Real-Time Listeners |

Task 2.1 — Gmail API Integration (Fetch/List) Phase 2 · Week 3 · 2.1

Description

Register a Google Cloud project, enable the Gmail API, create OAuth 2.0 credentials, and implement the Gmail fetch function that retrieves message headers and snippets for new messages.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/email/gmail.js | Gmail provider module — fetchMessages(uid, accountDoc, maxResults) |
| functions/src/auth/tokenManager.js | OAuth token refresh helper — checks expiry, refreshes via Google token endpoint |
| functions/package.json | Add dependencies: googleapis@^140, google-auth-library@^9 |

APIs Used

| API / Service | Usage |
| --- | --- |
| Gmail API v1 | users.messages.list — q:'is:unread', maxResults param |
| Gmail API v1 | users.messages.get — format:'metadata', metadataHeaders:['From','Subject','Date','Message-ID'] |
| Google OAuth 2.0 | Token refresh endpoint: https://oauth2.googleapis.com/token |
| Firestore Admin SDK | Read accounts/{accountId} for stored OAuth tokens |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| accounts/{accountId}.accessToken | Read — decrypted for API call, never returned to client |
| accounts/{accountId}.refreshToken | Read — used to obtain new access token when expired |
| accounts/{accountId}.tokenExpiresAt | Read/Write — updated after token refresh |
| accounts/{accountId}.lastError | Write — stores error message if fetch fails |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js backend engineer. Implement the Gmail email fetch module for the AI-Powered Email Sorter Firebase Cloud Functions backend. File: functions/src/email/gmail.js Export one function: fetchMessages(uid, accountDoc, maxResults = 30) Parameters: uid: Firebase Auth UID of the requesting user accountDoc: Firestore document data for the Gmail account (contains encrypted tokens) maxResults: maximum messages to fetch (cap at 100) Implementation: 1. Decrypt accessToken from accountDoc using AES-256-GCM and ENCRYPTION_SECRET env var. Use Node.js built-in crypto module — no external crypto libraries. Encryption scheme: IV prepended to ciphertext, stored as hex string. 2. Check tokenExpiresAt. If within 5 minutes of expiry or already expired: POST to https://oauth2.googleapis.com/token with grant_type=refresh_token. Update Firestore accounts/{accountDoc.id} with new accessToken, tokenExpiresAt. Use the refreshed token for this request. 3. Initialise googleapis OAuth2Client with the access token. Call gmail.users.messages.list: userId: 'me' q: 'is:unread in:inbox' maxResults: maxResults 4. For each message ID returned, call gmail.users.messages.get: userId: 'me' id: messageId format: 'metadata' metadataHeaders: ['From', 'Subject', 'Date', 'Message-ID'] Extract: id, threadId, snippet, and header values. 5. Return array of normalised message objects: { providerId, provider:'gmail', accountId, from, fromName, subject, snippet (first 300 chars), receivedAt (Date from headers), threadId } Error handling: - HTTP 401: attempt one token refresh, retry. If still 401, throw with code 'auth_error'. - HTTP 429: throw with code 'rate_limit', message 'Gmail rate limit — try again shortly'. - Network errors: throw with code 'network_error'. - All errors must be catchable by the caller without crashing the sync function. Security: never log token values. Never return token values to the caller.

Task 2.2 — Cloud Function: syncEmails Phase 2 · Week 3 · 2.2

Description

Implement the main syncEmails Cloud Function that orchestrates fetching from all connected accounts, deduplicates against existing Firestore records, calls the classifier for each new message, and writes results to Firestore.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export syncEmails as HTTPS callable function |
| functions/src/email/sync.js | Core sync orchestration logic |
| functions/src/email/gmail.js | Used here — fetchMessages called per Gmail account |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Functions | functions.https.onCall — authenticated callable function |
| Firestore Admin SDK | Query accounts collection, batch write email documents |
| Claude API | Called via classifier/classify.js — implemented in Task 2.3 |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/accounts | Read all — filter by status:'connected' |
| users/{uid}/emails | Query by providerId to deduplicate — Write new email documents |
| users/{uid}/emails/{id}.folder | Written by classifier result |
| users/{uid}/emails/{id}.confidence | Written by classifier result (0.0–1.0) |
| users/{uid}/emails/{id}.classifiedBy | Written: 'rule' ¦ 'ai' ¦ 'user' |
| users/{uid} | Write lastSyncAt: serverTimestamp() on completion |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js Firebase Functions engineer. Implement the syncEmails Cloud Function for the AI-Powered Email Sorter. File: functions/src/email/sync.js — export runSync(uid, maxPerAccount) File: functions/src/index.js — export syncEmails as onCall wrapper syncEmails onCall function: 1. Call verifyToken(context) — throw unauthenticated if not signed in. 2. Extract uid from verified token. 3. Parse request.data.maxPerAccount (default 30, max 100). 4. Call runSync(uid, maxPerAccount). Return result. runSync(uid, maxPerAccount) implementation: 1. Fetch all documents from users/{uid}/accounts where status == 'connected'. 2. For each account, call the appropriate provider fetch function in parallel (Promise.allSettled — one account failure must not block others). Currently only gmail provider exists. Add a switch on account.provider. 3. Collect all fetched messages across all accounts into a flat array. 4. For each message: a. Check users/{uid}/emails for existing document with providerId == message.providerId. Skip if found (deduplication). b. Call classifyEmail(message, uid) from classifier/classify.js. Wrap in try/catch — on error, default to { folder:'uncategorized', confidence:0.0, classifiedBy:'ai' }. c. Build email document (full schema from SPEC-EMAILSORT-001 Section 5.2). d. Write to users/{uid}/emails/{message.providerId} using Admin SDK setDoc. 5. After all messages processed, update users/{uid}.lastSyncAt = serverTimestamp(). 6. For each account that errored, write error message to accounts/{id}.lastError. For successful accounts, clear lastError and update lastSyncAt. 7. Return: { synced: number, skipped: number, errors: [{ accountId, message }] } Performance: use Firestore batched writes (max 500 per batch) for email documents. Do not await each write individually — collect and batch commit. Timeout: set Functions timeout to 300 seconds (5 minutes) and memory to 512MB in index.js: exports.syncEmails = functions.runWith({timeoutSeconds:300, memory:'512MB'}) .https.onCall(...)

Task 2.3 — Claude Haiku Classifier Phase 2 · Week 4 · 2.3

Description

Implement the email classification module that calls the Anthropic Claude Haiku API, constructs the classification prompt with training context, parses the structured JSON response, and applies confidence thresholds.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/classifier/classify.js | Primary classification module — exported classifyEmail(message, uid) |
| functions/src/classifier/prompt.js | Prompt assembly — system prompt + dynamic user message builder |
| functions/package.json | Add dependency: @anthropic-ai/sdk@^0.20 |

APIs Used

| API / Service | Usage |
| --- | --- |
| Anthropic Claude API | POST /v1/messages — model: claude-haiku-4-5, max_tokens: 100 |
| Firestore Admin SDK | Read users/{uid}/trainingContext for cached training examples |
| Firestore Admin SDK | Read users/{uid}/rules where enabled==true, orderBy priority ASC |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| ANTHROPIC_API_KEY | Read from Firebase Functions secret / process.env |
| users/{uid}/trainingContext | Read — injected into classification prompt if exists |
| users/{uid}/rules | Read — applied before AI call in Task 4.3; stubbed here |
| Response: folder | One of: work¦students¦newsletters¦receipts¦personal¦spam¦uncategorized |
| Response: confidence | Float 0.0–1.0 — below 0.6 forces folder to uncategorized |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are an AI/ML engineer. Implement the email classification module for the AI-Powered Email Sorter using the Anthropic Claude API. File: functions/src/classifier/classify.js File: functions/src/classifier/prompt.js classify.js — export classifyEmail(message, uid): message: { from, fromName, subject, snippet } uid: used to fetch training context from Firestore Returns: { folder, confidence, classifiedBy: 'ai' } prompt.js — export buildPrompt(message, trainingContext, rules): System prompt (static — do not modify at runtime): 'You are an email classification engine. Classify the email into exactly one of these folders: work, students, newsletters, receipts, personal, spam, uncategorized. Respond with ONLY valid JSON in this exact format: {"folder": "<folder_id>", "confidence": <0.0 to 1.0>} Rules: No explanation. No markdown. No preamble. No extra fields. If confidence is below 0.6, set folder to uncategorized regardless of your assessment.' User message (dynamic): Line 1: 'From: {from} ({fromName})' Line 2: 'Subject: {subject}' Line 3: 'Snippet: {snippet (max 300 chars)}' If trainingContext exists and has entries (max 20 most recent): blank line 'Recent corrections (learn from these):' for each: '{from_snippet} ¦ {subject_snippet} -> {folder}' If rules exist: blank line 'Active classification rules (higher priority than your assessment):' for each enabled rule: '- {rule.description}' classify.js implementation: 1. Fetch trainingContext document from Firestore (catch error, default to null). 2. Fetch enabled rules from Firestore ordered by priority ASC (catch error, default []). 3. Build prompt using buildPrompt(message, trainingContext, rules). 4. Call Anthropic API: model: 'claude-haiku-4-5' max_tokens: 100 messages: [{ role: 'user', content: userMessage }] system: systemPrompt 5. Extract response text. Strip any accidental markdown fences. 6. Parse JSON. Validate folder is one of the 7 valid values. If invalid folder: set folder='uncategorized', confidence=0.0. 7. Apply confidence threshold: if confidence < 0.6, set folder='uncategorized'. 8. Return { folder, confidence, classifiedBy: 'ai' }. Error handling: Any API error, timeout, or JSON parse failure: return { folder: 'uncategorized', confidence: 0.0, classifiedBy: 'ai' } Log warning with message.subject (not message content) for debugging. Never throw — the caller must always receive a valid classification object. Cost note: at ~400 input + 20 output tokens per call at Haiku pricing, 30 emails costs approximately $0.004. Log token usage in development.

Task 2.4 — Confidence Scoring + Thresholds Phase 2 · Week 4 · 2.4

Description

Implement the confidence threshold logic, define the four indicator states (green/amber/red/blue), and ensure the scoring is applied consistently across both the classifier and the sync function.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/classifier/classify.js | Threshold enforcement already in place from 2.3 — verify correctness |
| functions/src/classifier/confidence.js | Utility: getConfidenceLevel(score, classifiedBy) → 'high'¦'medium'¦'low'¦'rule' |
| frontend/src/components/ConfidenceBadge.jsx | Visual badge component — renders colour-coded confidence indicator |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| emails/{id}.confidence | 0.0–1.0 float stored in Firestore — source of truth for all UI |
| emails/{id}.classifiedBy | 'rule'¦'ai'¦'user' — determines badge colour |
| Threshold: high | confidence >= 0.8 — green badge |
| Threshold: medium | 0.6 <= confidence < 0.8 — amber badge |
| Threshold: low / forced | confidence < 0.6 — red badge, folder forced to uncategorized |
| Threshold: rule | classifiedBy == 'rule', confidence == 1.0 — blue badge |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React and Node.js engineer. Implement the confidence scoring system for the AI-Powered Email Sorter. 1. functions/src/classifier/confidence.js: Export getConfidenceLevel(confidence, classifiedBy): Returns one of: 'rule' ¦ 'high' ¦ 'medium' ¦ 'low' Logic: if classifiedBy === 'rule': return 'rule' if classifiedBy === 'user': return 'user' // manually moved by user if confidence >= 0.8: return 'high' if confidence >= 0.6: return 'medium' return 'low' // this email is in uncategorized folder Export getConfidenceDisplay(confidence, classifiedBy): Returns { level, label, color, bgColor } level: from getConfidenceLevel() label: 'Rule Match' ¦ 'High' ¦ 'Medium' ¦ 'Low Confidence' ¦ 'Manual' color (text): 'FFFFFF' for all bgColor: rule='1565C0', high='2E7D32', medium='E65100', low='C62828', user='6A1B9A' 2. frontend/src/components/ConfidenceBadge.jsx: Props: confidence (number), classifiedBy (string) Renders a small pill badge with: - Background colour from getConfidenceDisplay() - Icon: ⬡ for rule, ● for high, ◑ for medium, ○ for low, ✎ for user - Label text from getConfidenceDisplay() - Percentage: show '({Math.round(confidence * 100)}%)' for ai-classified emails Do not show percentage for rule-matched or user-moved emails Style: inline-flex, border-radius 12px, padding 2px 8px, font-size 11px 3. Integrate ConfidenceBadge into EmailListItem (stub for now — implement fully in Task 2.5) Each email row in the list should show the confidence badge to the right of the subject. Testing: write a simple test in functions/src/classifier/confidence.test.js covering all threshold boundaries: 0.0, 0.59, 0.6, 0.79, 0.8, 1.0 and classifiedBy values: 'rule', 'ai', 'user'

Task 2.5 — React Folder View + Email List UI Phase 2 · Week 4 · 2.5

Description

Build the complete email list view with real data from Firestore: folder item counts, email rows with sender, subject, date, snippet, and confidence badge, and an empty-state design for folders with no emails.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/components/EmailListPanel.jsx | Complete implementation — replaces stub from Task 1.5 |
| frontend/src/components/EmailListItem.jsx | Single email row — from, subject, date, snippet, confidence badge |
| frontend/src/components/FolderItem.jsx | Update to show real unread count from Firestore |
| frontend/src/components/FolderActionBar.jsx | Folder action buttons — delete all, mark all read (enabled stubs) |
| frontend/src/context/EmailContext.jsx | Firestore listeners — emails by folder, sync function wrapper |
| frontend/src/services/functions.js | Cloud Function call wrapper — callFunction(name, data, idToken) |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firestore SDK | onSnapshot — real-time listener on emails where folder==activeFolder |
| Cloud Functions | syncEmails callable — triggered by Sync button in TopBar |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/emails | onSnapshot query: folder==activeFolder, orderBy receivedAt DESC, limit 50 |
| users/{uid}/emails | Pagination: startAfter(lastDoc) for Load More |
| EmailContext state | { emails: [], loading: bool, syncing: bool, syncError: string¦null } |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React engineer. Build the email list UI for the AI-Powered Email Sorter. Use Firebase Firestore real-time listeners (onSnapshot) for live updates. 1. frontend/src/context/EmailContext.jsx: Provider state: emails (array), loading, syncing, syncError, lastSyncAt On activeFolder change (from FolderContext): detach previous listener, attach new one. Listener query: collection users/{uid}/emails where('folder', '==', activeFolder) orderBy('receivedAt', 'desc') limit(50) On snapshot: update emails state. Set loading:false after first snapshot. Detach listener on component unmount or folder change. syncEmails(): call Cloud Function syncEmails via HTTPS callable. Set syncing:true before call, syncing:false after. On error: set syncError with user-friendly message. 2. frontend/src/services/functions.js: Export callFunction(name, data): Use Firebase Functions httpsCallable(functions, name). Attach current user's ID token automatically (Firebase SDK does this). Return result.data. 3. frontend/src/components/EmailListPanel.jsx: Header: folder name + email count badge FolderActionBar below header Loading state: 3 skeleton rows (animated grey placeholder bars) Empty state: folder icon (large, muted), 'No emails in this folder', 'Run a sync to fetch new emails' with arrow pointing to sync button Email list: map emails to EmailListItem components Load More button at bottom (only if 50 emails loaded — implies more exist) 4. frontend/src/components/EmailListItem.jsx: Layout (single row, 72px height, full width, cursor pointer): Left: unread indicator dot (blue if isRead==false) Main: sender name (bold if unread) + date (right-aligned) subject line (bold if unread, truncated with ellipsis at 1 line) snippet (muted, truncated at 1 line) Right: ConfidenceBadge Active state: light blue background when email is selected Hover state: very light grey background On click: setActiveEmail(email.id) + navigate to /folder/{folderId}/{emailId} 5. FolderItem unread counts: Use a separate Firestore query per folder: count of emails where isRead==false. Use getCountFromServer() (Firestore aggregate query) — do not download all documents. Update counts when user returns to the app (on focus event).

Task 2.6 — Firestore Real-Time Listeners Phase 2 · Week 5 · 2.6

Description

Harden the real-time listener architecture — ensure listeners are properly attached and detached, handle offline/reconnect scenarios, implement the folder count aggregate queries, and add connection state indication to the UI.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/context/EmailContext.jsx | Hardened listener management — ref-based cleanup |
| frontend/src/hooks/useFolderCounts.js | Custom hook — returns { folderId: count } object for all 7 folders |
| frontend/src/hooks/useConnectionState.js | Custom hook — detects Firestore online/offline state |
| frontend/src/components/TopBar.jsx | Add connection state indicator (green dot / amber dot) |
| frontend/src/components/Sidebar.jsx | Pass folder counts from useFolderCounts to FolderItem components |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firestore SDK | onSnapshot with error handler — detects permission errors vs network errors |
| Firestore SDK | getCountFromServer — aggregate count queries for folder badges |
| Firestore SDK | enableIndexedDbPersistence — offline support |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Listener lifecycle | Attached: on auth + folder change. Detached: on auth signout, folder change, unmount |
| Folder counts | Aggregate query: count of emails per folder — refreshed on sync completion |
| Offline state | Cached Firestore data served from IndexedDB when offline |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React and Firebase engineer specialising in real-time data patterns. Harden the Firestore listener architecture for the AI-Powered Email Sorter. 1. frontend/src/hooks/useFolderCounts.js: Custom hook that returns an object: { work: n, students: n, ... } for all 7 folders. Use Promise.all with getCountFromServer() for each folder — one aggregate query each. Do not use onSnapshot for counts (too many listener connections). Refresh counts: on initial load, after syncEmails completes, and on window focus. While loading: return { work: null, students: null, ... } (null = show skeleton) 2. frontend/src/hooks/useConnectionState.js: Use Firestore's '.info/connected' equivalent for Firebase Realtime DB, OR detect connectivity by catching onSnapshot errors with code 'unavailable'. Return: { online: bool, lastOnlineAt: Date¦null } 3. EmailContext.jsx hardening: Store unsubscribe function in a useRef — never a useState (avoids re-render on change). Cleanup pattern: const unsubRef = useRef(null); useEffect(() => { if (unsubRef.current) unsubRef.current(); // detach previous unsubRef.current = onSnapshot(query, handler, errorHandler); return () => { if (unsubRef.current) unsubRef.current(); }; }, [activeFolder, user]); onSnapshot errorHandler: distinguish between: code 'permission-denied': sign out user, show 'Session expired — please sign in again' code 'unavailable': show offline indicator, continue with cached data other: log error, show 'Unable to load emails — please refresh' 4. Offline persistence: In frontend/src/firebase.js, after Firestore initialisation: enableIndexedDbPersistence(db).catch(err => { if (err.code === 'failed-precondition') console.warn('Multiple tabs open'); if (err.code === 'unimplemented') console.warn('Browser does not support persistence'); }); 5. TopBar connection indicator: Small dot (8px circle) to the left of the Sync button. Green (#4CAF50) when online, amber (#FF9800) when offline. Tooltip on hover: 'Connected' or 'Offline — showing cached data'.

PHASE 3 Full Email Actions Weeks 6–7 · 6 Tasks

Phase 3 builds the complete set of actions a user can perform on individual emails and folders. With Phase 2 delivering the read-only sorted view, Phase 3 makes the application interactive and genuinely useful for daily email management.

The six tasks in this phase cover reading an email's full body on demand, moving emails between folders with that action recorded as a training signal for the AI, deleting emails with writeback to Gmail's Trash, replying and forwarding via the Gmail API, flagging individual emails as training examples, and bulk folder operations.

A key engineering discipline in this phase is the delete contract: deletion must succeed at the source mailbox before the Firestore document is removed. If the Gmail API call fails, the email stays in Firestore and an error is surfaced to the user. This prevents the inconsistency of data disappearing from the app but remaining in the inbox.

## Task Summary

| Task ID | Week | Task Name |
| --- | --- | --- |
| 3.1 | Week 6 | Read Full Email Body (On Demand) |
| 3.2 | Week 6 | Recategorise Email + Training Signal |
| 3.3 | Week 6 | Delete Email (Firestore + Gmail Trash) |
| 3.4 | Week 7 | Reply / Forward via Gmail API |
| 3.5 | Week 7 | Mark Email as Training Example |
| 3.6 | Week 7 | Folder Bulk Actions |

Task 3.1 — Read Full Email Body (On Demand) Phase 3 · Week 6 · 3.1

Description

Implement on-demand full body fetching — email bodies are not stored in Firestore on sync, only snippets. When a user opens an email, the full body is fetched from Gmail, cached in Firestore, and displayed.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export getEmailBody as new HTTPS callable function |
| functions/src/email/gmail.js | Add getMessageBody(accessToken, messageId) — fetches full MIME body |
| frontend/src/components/EmailDetailPanel.jsx | Full implementation — renders email header + body + action toolbar |
| frontend/src/components/EmailBody.jsx | Renders sanitised HTML or plain text body |

APIs Used

| API / Service | Usage |
| --- | --- |
| Gmail API v1 | users.messages.get — format:'full', extract text/plain or text/html parts |
| Firebase Functions | getEmailBody onCall — accepts { emailId, accountId } |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/emails/{id}.bodyText | Written on first open — cached to avoid repeated API calls |
| users/{uid}/emails/{id}.isRead | Set to true when email is opened |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js and React engineer. Implement on-demand email body fetching for the AI-Powered Email Sorter. functions/src/email/gmail.js — add getMessageBody(oauth2Client, messageId): Call gmail.users.messages.get with format:'full'. Parse MIME parts: prefer text/html, fall back to text/plain. Decode base64url encoded body data. Return: { bodyHtml: string¦null, bodyText: string } functions/src/index.js — export getEmailBody onCall: 1. verifyToken(context) → uid 2. Validate request.data: emailId (string), accountId (string) 3. Fetch email document from users/{uid}/emails/{emailId} Verify email.accountId matches request.data.accountId (security check) 4. If email.bodyText already populated: return it without calling Gmail API (cache hit — avoids redundant API calls) 5. Fetch account document, decrypt token 6. Call getMessageBody(oauth2Client, emailId) 7. Update Firestore: users/{uid}/emails/{emailId} { bodyText, isRead: true, readAt: serverTimestamp() } 8. Return { bodyHtml, bodyText } frontend/src/components/EmailDetailPanel.jsx: On email selection (emailId from URL params): 1. Look up email in EmailContext (already in memory from list) 2. If email.bodyText is null/empty: call getEmailBody Cloud Function Show loading skeleton while fetching 3. If email.bodyText is populated: render immediately (no API call) Layout: Top: sender, subject, date, account badge, ConfidenceBadge Action toolbar: Reply, Forward, Move, Delete, Flag Training (see Tasks 3.2–3.5) Body: EmailBody component frontend/src/components/EmailBody.jsx: Props: bodyHtml (string¦null), bodyText (string) If bodyHtml: render in a sandboxed iframe (sandbox='allow-same-origin') Set iframe srcdoc to bodyHtml. Fix iframe height to content height. Else: render bodyText in a <pre> with word-wrap:break-word Security: NEVER use dangerouslySetInnerHTML directly on bodyHtml without iframe sandbox.

Task 3.2 — Recategorise Email + Training Signal Phase 3 · Week 6 · 3.2

Description

Implement the move-to-folder action — updates the email's folder in Firestore and records a training signal document so the AI can learn from the correction.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export recategorizeEmail onCall |
| functions/src/email/recategorize.js | Recategorize logic + training signal writer |
| frontend/src/components/MoveFolderMenu.jsx | Dropdown showing 7 folder options for selected email |
| frontend/src/components/EmailActionMenu.jsx | Three-dot menu on EmailListItem — contains Move, Delete, Flag Training |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Functions | recategorizeEmail onCall — { emailId, targetFolder } |
| Firestore Admin SDK | Update emails/{id}.folder, write training/{id} document |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/emails/{id}.folder | Updated to targetFolder |
| users/{uid}/emails/{id}.classifiedBy | Set to 'user' |
| users/{uid}/emails/{id}.confidence | Set to 1.0 (user is certain) |
| users/{uid}/training/{id} | New document: emailId, snippet, fromAddress, subject, folder:'targetFolder', source:'recategorise', createdAt |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js and React engineer. Implement the email recategorisation feature for the AI-Powered Email Sorter, including training signal recording. functions/src/email/recategorize.js — export recategorizeEmail(uid, emailId, targetFolder): 1. Validate targetFolder is one of the 7 valid folder IDs. 2. Fetch email document from users/{uid}/emails/{emailId}. If not found: throw HttpsError('not-found', 'Email not found') 3. Firestore batch write: a. Update users/{uid}/emails/{emailId}: { folder: targetFolder, classifiedBy: 'user', confidence: 1.0, recategorizedAt: serverTimestamp() } b. Create users/{uid}/training/{auto-id}: { emailId, snippet: email.snippet, fromAddress: email.from, subject: email.subject, folder: targetFolder, source: 'recategorise', createdAt: serverTimestamp() } 4. Commit batch. 5. Return { success: true, newFolder: targetFolder } functions/src/index.js — export recategorizeEmail onCall: verifyToken → validate inputs → call recategorizeEmail → return result frontend/src/components/MoveFolderMenu.jsx: Props: emailId, currentFolder, onMoved Renders a dropdown with all 7 folders. Current folder greyed out with a checkmark. On selection: call recategorizeEmail Cloud Function. Show loading state on selected item while call is in progress. On success: call onMoved(newFolder) — parent removes email from current list. On error: show toast notification 'Failed to move email — please try again' UI feedback: The email should disappear from the current folder view immediately on move (optimistic update) and reappear if the Cloud Function returns an error. Implement optimistic update in EmailContext: remove email from local state immediately, restore on error.

Task 3.3 — Delete Email (Firestore + Gmail Trash) Phase 3 · Week 6 · 3.3

Description

Implement email deletion — moves the message to Gmail Trash via the API, then removes the Firestore document. If the Gmail API call fails, the Firestore document is preserved and an error is shown.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export deleteEmail onCall |
| functions/src/email/gmail.js | Add trashMessage(oauth2Client, messageId) |
| functions/src/email/delete.js | Delete orchestration — provider call then Firestore delete |
| frontend/src/components/DeleteConfirmDialog.jsx | Modal confirmation dialog — warns of permanent action |

APIs Used

| API / Service | Usage |
| --- | --- |
| Gmail API v1 | users.messages.trash — moves to Trash (recoverable for 30 days) |
| Firebase Functions | deleteEmail onCall — { emailId } |
| Firestore Admin SDK | Delete users/{uid}/emails/{emailId} after successful trash |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/emails/{emailId} | Deleted from Firestore only after successful Gmail trash call |
| Gmail Trash | Message moved to Trash — recoverable from Gmail UI for 30 days |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js and React engineer. Implement email deletion for the AI-Powered Email Sorter with strict source-first delete contract. Delete contract (CRITICAL): The Firestore document must ONLY be deleted AFTER the Gmail API trash call succeeds. If Gmail fails, Firestore is NOT touched. This prevents the user losing track of an email that still exists in their inbox. functions/src/email/delete.js — export deleteEmail(uid, emailId): 1. Fetch users/{uid}/emails/{emailId} — verify it exists and belongs to uid. 2. Fetch account document for email.accountId — get and decrypt access token. 3. Call provider-specific delete based on email.provider: gmail: await gmail.users.messages.trash({ userId:'me', id:email.providerId }) (outlook and imap: throw 'not_implemented' — handled in Tasks 5.4 and 6.4) 4. ONLY if step 3 succeeds: delete users/{uid}/emails/{emailId} from Firestore. 5. Return { success: true, providerId: email.providerId } Error handling: Gmail 404 (message already trashed/deleted in Gmail): Still delete Firestore document — source is already gone, clean up local record. Gmail 401/403: throw HttpsError('permission-denied', 'Gmail auth error — reconnect account') Gmail 429: throw HttpsError('resource-exhausted', 'Gmail rate limit — try again shortly') Any other Gmail error: throw HttpsError('internal', 'Could not delete from Gmail') Do NOT delete Firestore document. frontend/src/components/DeleteConfirmDialog.jsx: Modal dialog — triggered by Delete button in EmailDetailPanel and EmailActionMenu. Props: email (object), onConfirm, onCancel Show: 'Delete this email?' heading 'From: {email.from}' and 'Subject: {email.subject}' Warning: 'This will move the email to your Gmail Trash.' 'Emails in Trash are permanently deleted after 30 days.' Two buttons: 'Cancel' (secondary) and 'Move to Trash' (red, primary) On confirm: call deleteEmail Cloud Function. Show loading state on confirm button. On success: close dialog, remove email from EmailContext state (optimistic already done). On error: show error message inside dialog, keep dialog open.

Task 3.4 — Reply / Forward via Gmail API Phase 3 · Week 7 · 3.4

Description

Implement reply and forward functionality using the Gmail API to send messages via the user's authenticated Gmail account.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export replyEmail and forwardEmail onCall functions |
| functions/src/email/gmail.js | Add sendReply(oauth2Client, originalMessage, replyText) and forwardMessage(oauth2Client, originalMessage, toAddress, note) |
| frontend/src/components/ReplyForwardComposer.jsx | Inline composer below email body — toggled by Reply/Forward buttons |

APIs Used

| API / Service | Usage |
| --- | --- |
| Gmail API v1 | users.messages.send — RFC 2822 MIME message as base64url encoded string |
| Gmail API v1 | users.threads.get — fetch thread for In-Reply-To header construction |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Reply headers | In-Reply-To: original Message-ID, References: original Message-ID, Subject: Re: {original} |
| Forward headers | Subject: Fwd: {original}, body prefixed with forwarded message block |
| users/{uid}/emails/{id}.isRead | Set to true when reply/forward composer is opened |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js email engineer. Implement reply and forward via the Gmail API for the AI-Powered Email Sorter. functions/src/email/gmail.js — add two functions: sendReply(oauth2Client, { originalMessageId, originalFrom, originalSubject, originalDate, threadId, replyText, userEmail }): Build RFC 2822 MIME message string: From: {userEmail} To: {originalFrom} Subject: Re: {originalSubject} (do not add Re: if subject already starts with Re:) In-Reply-To: {originalMessageId} References: {originalMessageId} Content-Type: text/plain; charset=utf-8 (blank line) {replyText} (blank line) On {originalDate}, {originalFrom} wrote: > {truncated original snippet — max 500 chars} Encode as base64url. Call gmail.users.messages.send({ userId:'me', requestBody:{ raw, threadId } }) Return sent message ID. forwardMessage(oauth2Client, { originalMessageId, originalFrom, originalSubject, originalDate, originalBody, toAddress, noteText, userEmail }): Build RFC 2822 MIME message: To: {toAddress} Subject: Fwd: {originalSubject} Content-Type: text/plain; charset=utf-8 {noteText if provided} (blank line) ---------- Forwarded message ---------- From: {originalFrom} Date: {originalDate} Subject: {originalSubject} (blank line) {originalBody — max 2000 chars, truncate with '[truncated]' if longer} Encode and send (no threadId for forwards). frontend/src/components/ReplyForwardComposer.jsx: Props: email (object), mode ('reply'¦'forward'), onSent, onCancel For reply: To field pre-populated and read-only. For forward: To field empty and editable. Validate email format on blur. Textarea for message body (min 4 lines, auto-expand). Character count indicator. Send button + Cancel button. Loading state while Cloud Function is in progress. On success: show 'Email sent' toast, call onSent(), collapse composer. On error: show error in composer, do not collapse.

Task 3.5 — Mark Email as Training Example Phase 3 · Week 7 · 3.5

Description

Implement explicit training flagging — the user can mark any email as a training example for a specific folder, which writes a training document and updates the email's isTrainingExample flag.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export markTrainingExample onCall |
| functions/src/email/training.js | Training signal writer — reused by recategorize and explicit flag |
| frontend/src/components/FlagTrainingDialog.jsx | Dialog — lets user confirm folder assignment for training |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Functions | markTrainingExample onCall — { emailId, targetFolder } |
| Firestore Admin SDK | Update emails/{id}.isTrainingExample, write training/{id} |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/emails/{id}.isTrainingExample | Set to true |
| users/{uid}/emails/{id}.trainingFolder | Set to targetFolder |
| users/{uid}/training/{id} | New document: source:'explicit_flag', folder:targetFolder |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js and React engineer. Implement the training example flagging feature for the AI-Powered Email Sorter. functions/src/email/training.js — export writeTrainingSignal(uid, emailDoc, folder, source): Creates a training document at users/{uid}/training/{auto-id}: { emailId: emailDoc.id, snippet: emailDoc.snippet, fromAddress: emailDoc.from, subject: emailDoc.subject, folder: folder, source: source, // 'recategorise' ¦ 'explicit_flag' ¦ 'retrain_session' createdAt: serverTimestamp() } Also updates users/{uid}/emails/{emailDoc.id}: { isTrainingExample: true, trainingFolder: folder } Use Firestore batch write for atomicity. Export this function for reuse by recategorize.js (replace duplicated code in Task 3.2). functions/src/index.js — export markTrainingExample onCall: verifyToken → validate { emailId, targetFolder } Fetch email document. Call writeTrainingSignal(uid, emailDoc, targetFolder, 'explicit_flag'). Return { success: true, folder: targetFolder } frontend/src/components/FlagTrainingDialog.jsx: Props: email, onFlagged, onCancel Title: 'Flag as Training Example' Body: 'Help the AI learn. Confirm which folder this email belongs to.' Show current folder with checkmark. Show all 7 folders as selectable radio buttons with icons. Pre-select current folder (or trainingFolder if already flagged). If email is already flagged (isTrainingExample==true): show 'Already flagged as training for: {trainingFolder}' with option to change. Confirm button: 'Save Training Example' On confirm: call markTrainingExample, show success toast, close dialog.

Task 3.6 — Folder Bulk Actions Phase 3 · Week 7 · 3.6

Description

Implement folder-level bulk operations: delete all emails in a folder (with source mailbox writeback), mark all as read, and the UI components that trigger them with appropriate confirmation guards.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export deleteFolderEmails and markFolderRead onCall functions |
| functions/src/email/bulkActions.js | Bulk operation implementations |
| frontend/src/components/FolderActionBar.jsx | Complete implementation — enabled buttons with confirmation |
| frontend/src/components/BulkDeleteConfirmDialog.jsx | Confirmation dialog — shows count, warns of permanent action |

APIs Used

| API / Service | Usage |
| --- | --- |
| Gmail API v1 | users.messages.batchDelete or repeated trash calls — max 1000 per batch |
| Firebase Functions | deleteFolderEmails onCall — { folderId } |
| Firebase Functions | markFolderRead onCall — { folderId } |
| Firestore Admin SDK | Query all emails in folder, batch delete / batch update |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/emails | Query where folder==folderId — delete all or update isRead:true |
| Gmail Trash | All messages trashed in Gmail before Firestore documents deleted |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js and React engineer. Implement folder bulk actions for the AI-Powered Email Sorter. functions/src/email/bulkActions.js: Export deleteFolderEmails(uid, folderId): 1. Query all users/{uid}/emails where folder == folderId. Process in batches of 100 to avoid memory issues. 2. For each email, call provider-specific trash/delete function. Use Promise.allSettled per batch — individual failures logged but don't stop bulk op. 3. Collect successfully trashed email IDs. 4. Firestore batch delete all successfully trashed email documents. (Only delete Firestore docs for emails that were successfully trashed in Gmail) 5. Return { deleted: number, failed: number, errors: [{ subject, error }] } Export markFolderRead(uid, folderId): 1. Query all users/{uid}/emails where folder==folderId AND isRead==false. 2. Firestore batch update: isRead:true, readAt:serverTimestamp(). 3. Return { updated: number } NOTE: This is app-side only — do not call Gmail API to mark as read. The spec requires mark-as-read only in the app, not in the source mailbox. frontend/src/components/FolderActionBar.jsx (complete implementation): Three buttons: 'Delete All', 'Mark All Read', 'Retrain AI' (retrain in Task 4.4) Delete All: disabled if folder is empty. Show email count: 'Delete All (23)'. On click: open BulkDeleteConfirmDialog. Mark All Read: disabled if no unread emails. On click: call markFolderRead directly (no confirmation needed). Show loading spinner while in progress. frontend/src/components/BulkDeleteConfirmDialog.jsx: Title: 'Delete all emails in {folderName}?' Body: 'This will permanently move {count} emails to your Gmail Trash.' 'This action cannot be undone from this application.' Type-to-confirm: user must type 'DELETE' to enable the confirm button. Progress: show progress bar and count during deletion (stream updates via Firestore listener on the folder count decreasing). On complete: show summary '23 deleted, 0 failed' or list of failures.

PHASE 4 Rules Engine Weeks 8–9 · 4 Tasks

Phase 4 introduces the rules engine — a deterministic classification layer that runs before the Claude API on every sync. User-defined rules allow exact, repeatable classification without consuming AI tokens, and take priority over AI results with a confidence score of 1.0.

The rules engine design deliberately separates two concerns: rule parsing (a one-time Claude API call at save time that converts a natural-language rule into a structured matcher object) and rule evaluation (a pure JavaScript function that applies the stored matchers without any API call). This means the AI cost of the rules feature is paid once, at rule creation, not on every email processed.

Phase 4 also introduces the retrain-from-folder capability, which allows the user to select any folder and have the application rebuild the AI's training context from the emails flagged as training examples in that folder. This directly addresses the accuracy improvement loop specified in the requirements.

## Task Summary

| Task ID | Week | Task Name |
| --- | --- | --- |
| 4.1 | Week 8 | Rule CRUD UI |
| 4.2 | Week 8 | Rule Parser (One-Time Claude Call on Save) |
| 4.3 | Week 8 | Rule Engine in syncEmails (Pre-AI Filter) |
| 4.4 | Week 9 | Retrain from Folder (Training Context Builder) |

Task 4.1 — Rule CRUD UI Phase 4 · Week 8 · 4.1

Description

Build the Rules management page — create, edit, enable/disable, reorder, and delete user-defined classification rules through a dedicated UI.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/components/RulesPage.jsx | Rules management page — list of rules with controls |
| frontend/src/components/RuleListItem.jsx | Single rule row — description, folder badge, priority, enable toggle, edit/delete |
| frontend/src/components/RuleEditorDialog.jsx | Create/edit dialog — natural language rule input, target folder selector |
| frontend/src/components/Sidebar.jsx | Add Rules link to sidebar navigation |
| frontend/src/services/functions.js | Add saveRule, deleteRule, reorderRules function wrappers |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Functions | saveRule onCall — { ruleText, targetFolder, priority, ruleId? } |
| Firebase Functions | deleteRule onCall — { ruleId } |
| Firestore SDK | onSnapshot on users/{uid}/rules — real-time rule list |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/rules/{id}.description | Natural language rule text entered by user |
| users/{uid}/rules/{id}.targetFolder | Folder the rule assigns matching emails to |
| users/{uid}/rules/{id}.priority | Integer — lower number = higher priority, evaluated first |
| users/{uid}/rules/{id}.enabled | Boolean — disabled rules are skipped in engine |
| users/{uid}/rules/{id}.matchers | Parsed matcher objects — written by Cloud Function in Task 4.2 |
| users/{uid}/rules/{id}.createdAt | Timestamp — set on creation |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React engineer. Build the rules management UI for the AI-Powered Email Sorter. Page route: /rules — add to React Router and sidebar navigation. frontend/src/components/RulesPage.jsx: Header: 'Classification Rules' title + 'Add Rule' button (top right) Empty state: 'No rules yet. Rules are applied before AI classification.', 'Create a rule to always classify emails from a specific sender or with specific', 'subject keywords into a folder — without using AI tokens.' Rule list: onSnapshot listener on users/{uid}/rules ordered by priority ASC. Each rule: RuleListItem component. Drag-to-reorder: implement with mouse/touch drag on priority handle (≡ icon). On drop: call reorderRules Cloud Function with new priority order. frontend/src/components/RuleListItem.jsx: Left: drag handle (≡), priority number badge Centre: rule description text (bold), target folder badge (coloured), matchers summary (e.g. 'from: @university.ca OR subject contains: invoice') Right: enable/disable toggle switch, Edit button, Delete button Disabled rule: greyed out, toggle shows 'Disabled' Pending parse state (matchers null): show 'Parsing rule...' spinner frontend/src/components/RuleEditorDialog.jsx: Title: 'New Rule' or 'Edit Rule' Field 1: Textarea — 'Describe the rule in plain English' Placeholder: 'e.g. Emails from anyone at university.ca go to Students' Helper text: 'The AI will convert this to a classification rule automatically.' Field 2: Folder selector — dropdown of all 7 folders Preview: once saved and parsed, show the generated matchers in human-readable form Buttons: Cancel, Save Rule On save: call saveRule Cloud Function. Show 'Parsing rule...' while in progress. Validation: rule text required (min 10 chars), folder required.

Task 4.2 — Rule Parser (One-Time Claude Call on Save) Phase 4 · Week 8 · 4.2

Description

Implement the saveRule Cloud Function that accepts a natural-language rule, calls Claude once to parse it into a structured matcher object, and stores both the description and the parsed matchers in Firestore.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export saveRule and deleteRule onCall functions |
| functions/src/rules/parser.js | Rule parsing via Claude API — converts NL rule to matcher JSON |
| functions/src/rules/engine.js | Stub — evaluateRule(matchers, message) — implemented fully in Task 4.3 |

APIs Used

| API / Service | Usage |
| --- | --- |
| Anthropic Claude API | claude-haiku-4-5 — parse rule text into structured matcher JSON |
| Firebase Functions | saveRule onCall — { ruleText, targetFolder, priority, ruleId? } |
| Firestore Admin SDK | Create or update users/{uid}/rules/{id} |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/rules/{id}.matchers | Array of matcher objects: [{ field, operator, value }] |
| Matcher fields | from_address ¦ from_domain ¦ subject ¦ subject_keywords ¦ recipient |
| Matcher operators | contains ¦ not_contains ¦ equals ¦ starts_with ¦ ends_with ¦ matches_regex |
| Matcher logic | All matchers in array are AND'd. Multiple rules OR'd (first match wins) |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js engineer. Implement the rule parser Cloud Function for the AI-Powered Email Sorter rules engine. functions/src/rules/parser.js — export parseRule(ruleText, targetFolder): Call Claude Haiku with this system prompt: 'You are a rule parser for an email classification system. Convert the user-provided natural language rule into a JSON array of matcher objects.', 'Each matcher has: { field, operator, value }', 'field options: from_address, from_domain, subject, subject_keywords, recipient', 'operator options: contains, not_contains, equals, starts_with, ends_with', 'Return ONLY a valid JSON array. No explanation. No markdown. No extra fields.', 'Example input: Emails from anyone at university.ca', 'Example output: [{"field":"from_domain","operator":"equals","value":"university.ca"}]' User message: ruleText Parse JSON response. Validate each matcher has field, operator, value. Validate field and operator are from allowed sets. Strip any matchers with invalid fields/operators (do not throw). Return: { matchers: [...], parsedAt: new Date().toISOString() } functions/src/index.js — export saveRule onCall: 1. verifyToken → uid 2. Validate: ruleText (string, min 10 chars), targetFolder (valid folder id), priority (integer >= 1) 3. If ruleId provided: verify rule belongs to uid before updating. 4. Write rule document immediately with matchers: null, status: 'parsing' (so UI can show 'Parsing...' state right away) 5. Call parseRule(ruleText, targetFolder). 6. Update rule document: { matchers, status:'active', parsedAt } 7. Return { ruleId, matchers } Error handling: if parseRule fails or returns empty matchers array: Update rule with status:'parse_failed', matchers:null. Return error to client: 'Could not parse rule — please rephrase and try again.' functions/src/index.js — export deleteRule onCall: verifyToken → validate ruleId → verify ownership → delete document → return { success:true }

Task 4.3 — Rule Engine in syncEmails (Pre-AI Filter) Phase 4 · Week 8 · 4.3

Description

Implement the rule evaluation function and integrate it into the syncEmails flow so that rules are evaluated before any Claude API call — emails matching a rule are classified instantly at cost zero.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/rules/engine.js | Full implementation — evaluateRules(rules, message) → match¦null |
| functions/src/email/sync.js | Updated syncEmails — insert rule engine evaluation before classifier call |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firestore Admin SDK | Read users/{uid}/rules where enabled==true, orderBy priority ASC — cached per sync run |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Rule evaluation order | Rules sorted by priority ASC — first match wins, remaining rules skipped |
| emails/{id}.classifiedBy | Set to 'rule' when a rule matches (not 'ai') |
| emails/{id}.confidence | Set to 1.0 for rule matches |
| emails/{id}.matchedRuleId | ID of the rule that matched — stored for UI display |
| Claude API calls saved | One API call saved per email that matches a rule |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js engineer. Implement the rule evaluation engine and integrate it into the syncEmails flow for the AI-Powered Email Sorter. functions/src/rules/engine.js — export evaluateRules(rules, message): rules: array of rule documents from Firestore (already filtered enabled==true, ordered by priority ASC) message: { from, subject, snippet } (normalised message object from provider fetch) Returns: { folder, ruleId, ruleName } if a rule matches, or null if no match. For each rule (in priority order): If rule.matchers is null or empty: skip. Evaluate ALL matchers in rule.matchers array against message (AND logic). If ALL matchers pass: return { folder: rule.targetFolder, ruleId: rule.id, ruleName: rule.description } If any matcher fails: continue to next rule. If no rule matches: return null. Matcher evaluation (evaluateMatcher(matcher, message)): field mapping: from_address → message.from (full email string) from_domain → extract domain from message.from subject → message.subject subject_keywords → message.subject (check each keyword separately) recipient → message.to (if available, else skip matcher) operator evaluation (all case-insensitive string comparison): contains: value in field not_contains: value NOT in field equals: field === value starts_with: field.startsWith(value) ends_with: field.endsWith(value) On any evaluation error (missing field etc): return false for that matcher. functions/src/email/sync.js — update runSync() classification step: Before the current classifyEmail() call, add: 1. Fetch rules once per sync run (not per email): load all enabled rules ordered by priority ASC. Cache in a local variable. 2. Call evaluateRules(cachedRules, message). 3. If match returned: classification = { folder: match.folder, confidence: 1.0, classifiedBy: 'rule', matchedRuleId: match.ruleId } Skip the Claude API call entirely. 4. If no match: proceed to Claude API call as before. Add logging: log count of rule-matched vs AI-classified emails per sync run. This data is useful for monitoring rule effectiveness.

Task 4.4 — Retrain from Folder (Training Context Builder) Phase 4 · Week 9 · 4.4

Description

Implement the retrain-from-folder feature that reads all training examples from a folder, assembles them into a training context document, and stores it in Firestore to be injected into future classification prompts.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export retrainFromFolder onCall |
| functions/src/classifier/retrain.js | Training context builder — reads training docs, assembles prompt fragment |
| frontend/src/components/FolderActionBar.jsx | Enable Retrain AI button — calls retrainFromFolder |
| frontend/src/components/RetrainDialog.jsx | Confirmation + progress dialog for retrain operation |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Functions | retrainFromFolder onCall — { folderId } or null for all folders |
| Firestore Admin SDK | Read users/{uid}/training where folder==folderId, orderBy createdAt DESC, limit 50 |
| Firestore Admin SDK | Write users/{uid}/trainingContext — single document, overwrites previous |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/training | Read — up to 50 most recent training signals per folder |
| users/{uid}/trainingContext.contextString | Written — formatted string injected into Claude prompt |
| users/{uid}/trainingContext.builtAt | Written — timestamp of last retrain |
| users/{uid}/trainingContext.signalCount | Written — number of training signals included |
| Claude prompt injection | trainingContext.contextString injected in Task 2.3 classify.js |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js engineer. Implement the training context builder for the AI-Powered Email Sorter AI retraining feature. functions/src/classifier/retrain.js — export buildTrainingContext(uid): 1. Fetch all training documents from users/{uid}/training orderBy createdAt DESC, limit 100. 2. Group by folder. For each folder, keep the 20 most recent signals. 3. Build a formatted context string: '=== Training Examples (learn from these classifications) ===\n' For each folder group: '--- {folderName} ---\n' For each signal: 'From: {fromAddress} ¦ Subject: {subject} -> {folder}\n' 4. Write to users/{uid}/trainingContext: { contextString, builtAt: serverTimestamp(), signalCount: total signals included, folderBreakdown: { work: n, students: n, ... } } 5. Return { signalCount, folderBreakdown } functions/src/index.js — export retrainFromFolder onCall: verifyToken → uid Call buildTrainingContext(uid). Return { signalCount, folderBreakdown, builtAt: new Date().toISOString() } frontend/src/components/RetrainDialog.jsx: Triggered by 'Retrain AI' button in FolderActionBar (any folder). Title: 'Rebuild AI Training Context' Body: 'The AI will be updated with your corrections and flagged training examples.' Show current training signal count from Firestore if available. Two buttons: Cancel, 'Retrain Now' On confirm: call retrainFromFolder Cloud Function. Show progress: 'Building training context...' On success: show summary: 'Training context updated.' '{signalCount} examples across {folderCount} folders.' 'New emails will be classified using this updated context.' On error: show error message, suggest checking training examples exist. Note: The training context is injected into the Claude classification prompt in functions/src/classifier/classify.js (already implemented in Task 2.3). No changes to classify.js are needed — it already reads trainingContext from Firestore.

PHASE 5 Outlook Integration Weeks 10–11 · 5 Tasks

Phase 5 extends the application to support Microsoft 365 and Outlook.com accounts via the Microsoft Graph API. The architecture established for Gmail in Phase 2 is deliberately provider-agnostic, so adding Outlook requires implementing the provider module, handling Microsoft's OAuth flow, and wiring the new provider into the existing sync, delete, and reply/forward paths.

Microsoft OAuth uses the MSAL (Microsoft Authentication Library) flow rather than Google's OAuth2Client. The token management pattern is identical in concept — acquire tokens, store encrypted in Firestore, refresh before expiry — but the implementation details differ. Microsoft access tokens expire in one hour; refresh tokens in Outlook accounts last 90 days but in enterprise accounts may be restricted by tenant policy.

All five tasks in this phase follow the same extend-not-replace principle: existing Gmail functionality must remain fully operational, and the new Outlook code paths are activated only when email.provider === 'outlook'.

## Task Summary

| Task ID | Week | Task Name |
| --- | --- | --- |
| 5.1 | Week 10 | Microsoft Entra App Registration |
| 5.2 | Week 10 | Graph API Token Management (MSAL) |
| 5.3 | Week 11 | Outlook Message Fetch + Classification |
| 5.4 | Week 11 | Outlook Delete (Deleted Items Folder) |
| 5.5 | Week 11 | Reply / Forward via Microsoft Graph API |

Task 5.1 — Microsoft Entra App Registration Phase 5 · Week 10 · 5.1

Description

Register the application in Microsoft Entra (Azure AD), configure the required Graph API permissions, and obtain the client ID and tenant configuration needed for the MSAL OAuth flow.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/.env.example | REACT_APP_MS_CLIENT_ID already defined — populate with Entra client ID |
| functions/.env.example | MS_CLIENT_SECRET — confidential client secret for token exchange |
| functions/src/auth/microsoftOAuth.js | MSAL token exchange helper — auth code → access + refresh tokens |

APIs Used

| API / Service | Usage |
| --- | --- |
| Microsoft Entra (Azure AD) | App registration, API permissions, redirect URI configuration |
| Microsoft Graph API | Required scopes: Mail.ReadWrite, offline_access, User.Read |
| Microsoft Identity Platform | OAuth 2.0 auth code flow with PKCE |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| REACT_APP_MS_CLIENT_ID | Public client ID — safe in frontend bundle |
| MS_CLIENT_SECRET | Confidential — Firebase Function secret only, never in frontend |
| Redirect URI | Must match exactly in Entra registration: https://{username}.github.io/email-sorter/auth/microsoft/callback |
| Tenant | common — supports both personal Outlook and work/school Microsoft 365 accounts |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Microsoft identity platform engineer. Provide complete step-by-step instructions to register the AI-Powered Email Sorter in Microsoft Entra. 1. AZURE PORTAL — APP REGISTRATION: Navigate to portal.azure.com > Microsoft Entra ID > App registrations > New registration. Name: 'AI-Powered Email Sorter' Supported account types: 'Accounts in any organizational directory and personal Microsoft accounts' Redirect URI: Single-page application (SPA) type, URL: https://{username}.github.io/email-sorter/auth/microsoft/callback Click Register. 2. REQUIRED API PERMISSIONS: API Permissions > Add a permission > Microsoft Graph > Delegated permissions: Add: Mail.ReadWrite, Mail.Send, offline_access, User.Read Click 'Grant admin consent' (required for offline_access). 3. AUTHENTICATION SETTINGS: Authentication > Implicit grant: enable 'Access tokens' and 'ID tokens'. Add localhost redirect URI for development: http://localhost:3000/auth/microsoft/callback (SPA type) 4. SECRET (for Functions token exchange): Certificates & secrets > New client secret. Description: 'email-sorter-functions', Expires: 24 months. Copy secret value immediately — it is only shown once. Store as Firebase secret: firebase functions:secrets:set MS_CLIENT_SECRET 5. RECORD FOR ENVIRONMENT VARIABLES: From Overview page, record: Application (client) ID → REACT_APP_MS_CLIENT_ID and GitHub Secret Directory (tenant) ID → use 'common' for multi-tenant 6. functions/src/auth/microsoftOAuth.js: Export exchangeCodeForTokens(authCode, redirectUri): POST to https://login.microsoftonline.com/common/oauth2/v2.0/token Body: grant_type=authorization_code, code=authCode, redirect_uri=redirectUri, client_id=process.env.MS_CLIENT_ID, client_secret=process.env.MS_CLIENT_SECRET, scope=Mail.ReadWrite Mail.Send offline_access User.Read Return: { accessToken, refreshToken, expiresAt, userEmail, displayName } Export refreshAccessToken(refreshToken): POST to same endpoint with grant_type=refresh_token. Return: { accessToken, expiresAt }

Task 5.2 — Graph API Token Management (MSAL) Phase 5 · Week 10 · 5.2

Description

Implement the Microsoft OAuth connect flow in the frontend — the user clicks 'Connect Outlook', authorises via Microsoft login, the auth code is exchanged for tokens in a Cloud Function, and the encrypted tokens are stored in Firestore.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export connectOutlook onCall — handles auth code exchange |
| frontend/src/components/AddAccountPage.jsx | Account connection UI — lists connected accounts, 'Add Account' options |
| frontend/src/components/MicrosoftConnectButton.jsx | OAuth initiation button — builds MSAL auth URL, opens popup |
| functions/src/auth/tokenManager.js | Add refreshMicrosoftToken() alongside existing refreshGoogleToken() |

APIs Used

| API / Service | Usage |
| --- | --- |
| Microsoft Identity Platform | Auth code flow: GET /authorize → POST /token |
| Microsoft Graph API | GET /me — verify token works, fetch display name and email |
| Firebase Functions | connectOutlook onCall — { authCode, redirectUri } |
| Firestore Admin SDK | Create users/{uid}/accounts/{id} with encrypted tokens |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| accounts/{id}.provider | Set to 'outlook' |
| accounts/{id}.accessToken | AES-256-GCM encrypted Microsoft access token |
| accounts/{id}.refreshToken | AES-256-GCM encrypted Microsoft refresh token |
| accounts/{id}.tokenExpiresAt | ISO timestamp — Microsoft tokens expire in 1 hour |
| accounts/{id}.email | Outlook email address from /me Graph call |
| accounts/{id}.status | Set to 'connected' on success |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React and Node.js OAuth engineer. Implement the Microsoft Outlook account connection flow for the AI-Powered Email Sorter. Frontend OAuth flow (popup-based, consistent with Gmail connect): frontend/src/components/MicrosoftConnectButton.jsx: On click, construct Microsoft auth URL: Base: https://login.microsoftonline.com/common/oauth2/v2.0/authorize Params: client_id, response_type=code, redirect_uri (must match Entra registration), scope=Mail.ReadWrite Mail.Send offline_access User.Read, response_mode=query, state={random nonce for CSRF protection}, prompt=select_account Open in popup window (600x700px). Listen for postMessage from popup with auth code. On code received: call connectOutlook Cloud Function with { authCode, redirectUri }. Show loading state while Function executes. On success: show 'Outlook connected: {email}', close popup, refresh account list. On error: show specific error message. Popup callback page (frontend/public/auth/microsoft/callback.html): This is a static HTML file (not a React route — must work without JS bundle). Extract 'code' from URL query params. Call window.opener.postMessage({ code }, window.location.origin). Show 'Connecting your account...' and close window. functions/src/index.js — export connectOutlook onCall: 1. verifyToken → uid 2. Validate: authCode (string), redirectUri (string) 3. Call exchangeCodeForTokens(authCode, redirectUri) from microsoftOAuth.js. 4. Call GET https://graph.microsoft.com/v1.0/me with access token. Extract: mail (or userPrincipalName), displayName. 5. Encrypt accessToken and refreshToken using AES-256-GCM. 6. Write to users/{uid}/accounts/{auto-id}: { provider:'outlook', email, displayName, accessToken:encrypted, refreshToken:encrypted, tokenExpiresAt, status:'connected', connectedAt:serverTimestamp() } 7. Return { success:true, email, displayName }

Task 5.3 — Outlook Message Fetch + Classification Phase 5 · Week 11 · 5.3

Description

Implement the Outlook provider fetch module using Microsoft Graph API, and wire it into the syncEmails function alongside the existing Gmail provider.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/email/outlook.js | Outlook provider module — fetchMessages(uid, accountDoc, maxResults) |
| functions/src/email/sync.js | Add 'outlook' case to provider switch in runSync() |

APIs Used

| API / Service | Usage |
| --- | --- |
| Microsoft Graph API | GET /me/mailFolders/inbox/messages — query unread messages |
| Microsoft Graph API | $select=id,subject,from,receivedDateTime,bodyPreview,conversationId |
| Microsoft Graph API | $filter=isRead eq false&$top={maxResults}&$orderby=receivedDateTime desc |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| emails/{id}.provider | Set to 'outlook' |
| emails/{id}.providerId | Microsoft message ID (immutable, used for dedup) |
| emails/{id}.threadId | conversationId from Graph API |
| emails/{id}.snippet | bodyPreview from Graph API (first 255 chars) |
| accounts/{id}.lastSyncAt | Updated after successful fetch |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js engineer. Implement the Microsoft Graph email fetch module for the AI-Powered Email Sorter. functions/src/email/outlook.js — export fetchMessages(uid, accountDoc, maxResults): Same signature and return shape as gmail.js fetchMessages(). This is critical — the sync function must be able to call either provider interchangeably. 1. Decrypt accessToken using AES-256-GCM and ENCRYPTION_SECRET. 2. Check tokenExpiresAt. If within 5 minutes: call refreshMicrosoftToken(refreshToken) from tokenManager.js. Update Firestore with new token. 3. GET https://graph.microsoft.com/v1.0/me/mailFolders/inbox/messages Headers: Authorization: Bearer {accessToken} Query params: $select=id,subject,from,receivedDateTime,bodyPreview,conversationId,isRead $filter=isRead eq false $top={maxResults} $orderby=receivedDateTime desc 4. Map response to normalised message format: { providerId: msg.id, provider: 'outlook', accountId: accountDoc.id, from: msg.from.emailAddress.address, fromName: msg.from.emailAddress.name, subject: msg.subject, snippet: msg.bodyPreview.substring(0, 300), receivedAt: new Date(msg.receivedDateTime), threadId: msg.conversationId } 5. Return array of normalised messages. Error handling: identical pattern to gmail.js. 401 → attempt one token refresh, retry. Still 401 → throw auth_error. 429 → throw rate_limit. Network error → throw network_error. functions/src/email/sync.js — add 'outlook' to provider switch: case 'outlook': messages = await fetchOutlookMessages(uid, account, maxPerAccount); break; Import fetchMessages as fetchOutlookMessages from './outlook.js'. Verify: after implementation, a connected Outlook account should appear in the accounts list and sync correctly alongside Gmail accounts in a single sync run.

Task 5.4 — Outlook Delete (Deleted Items Folder) Phase 5 · Week 11 · 5.4

Description

Implement Outlook email deletion via the Microsoft Graph API, which moves messages to the Deleted Items folder rather than permanent deletion — consistent with Gmail Trash behaviour.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/email/outlook.js | Add moveToDeletedItems(accessToken, messageId) |
| functions/src/email/delete.js | Add 'outlook' case to provider switch in deleteEmail() |

APIs Used

| API / Service | Usage |
| --- | --- |
| Microsoft Graph API | POST /me/messages/{id}/move — body: { destinationId: 'deleteditems' } |
| Firebase Functions | Existing deleteEmail onCall — no signature change needed |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Outlook Deleted Items | Message moved to Deleted Items — equivalent to Gmail Trash |
| users/{uid}/emails/{id} | Deleted from Firestore only after successful Graph API move |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js engineer. Implement Outlook email deletion for the AI-Powered Email Sorter using the Microsoft Graph API. functions/src/email/outlook.js — add moveToDeletedItems(oauth2Headers, messageId): oauth2Headers: { Authorization: 'Bearer {accessToken}' } POST https://graph.microsoft.com/v1.0/me/messages/{messageId}/move Body: JSON.stringify({ destinationId: 'deleteditems' }) Headers: oauth2Headers + { 'Content-Type': 'application/json' } On 200/201: return { success: true } On 404: return { success: true, alreadyDeleted: true } (Message already gone from inbox — treat as success, clean up Firestore) On 401: throw { code: 'auth_error' } On 429: throw { code: 'rate_limit' } Other: throw { code: 'graph_error', status: response.status } functions/src/email/delete.js — add outlook case: case 'outlook': const headers = { Authorization: `Bearer ${decryptedToken}` }; await moveToDeletedItems(headers, email.providerId); break; The existing delete contract from Task 3.3 applies identically: Firestore document deleted ONLY after successful Graph API call. 404 from Graph → still delete Firestore document. Other errors → do NOT delete Firestore document, throw to client. Update DeleteConfirmDialog.jsx warning text: For Gmail accounts: 'This will move the email to your Gmail Trash.' For Outlook accounts: 'This will move the email to your Outlook Deleted Items.' Determine provider from email.provider field.

Task 5.5 — Reply / Forward via Microsoft Graph API Phase 5 · Week 11 · 5.5

Description

Implement reply and forward for Outlook accounts using the Microsoft Graph API createReply, createForward, and send endpoints.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/email/outlook.js | Add sendReply() and forwardMessage() for Graph API |
| functions/src/index.js | Update replyEmail and forwardEmail to route by email.provider |

APIs Used

| API / Service | Usage |
| --- | --- |
| Microsoft Graph API | POST /me/messages/{id}/createReply — creates reply draft |
| Microsoft Graph API | POST /me/messages/{replyDraftId}/send — sends the draft |
| Microsoft Graph API | POST /me/messages/{id}/createForward — creates forward draft |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Reply/forward threading | Graph API handles threading automatically via createReply endpoint |
| users/{uid}/emails/{id}.isRead | Set to true when reply/forward composer is opened |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js engineer. Implement reply and forward for Outlook accounts using the Microsoft Graph API for the AI-Powered Email Sorter. functions/src/email/outlook.js — add two functions: sendReply(accessToken, { originalProviderId, replyText }): Step 1: POST https://graph.microsoft.com/v1.0/me/messages/{originalProviderId}/createReply Body: { comment: replyText } Headers: Authorization: Bearer {accessToken}, Content-Type: application/json Response contains draft message with id. Step 2: POST https://graph.microsoft.com/v1.0/me/messages/{draftId}/send Body: empty {} On 202 (Accepted): return { success: true } Handle errors: 401 → auth_error, 429 → rate_limit, other → graph_send_error forwardMessage(accessToken, { originalProviderId, toAddress, noteText }): Validate toAddress is a valid email format before API call. POST https://graph.microsoft.com/v1.0/me/messages/{originalProviderId}/createForward Body: { comment: noteText ¦¦ '', toRecipients: [{ emailAddress: { address: toAddress } }] } Response contains draft id. POST https://graph.microsoft.com/v1.0/me/messages/{draftId}/send On 202: return { success: true } functions/src/index.js — update replyEmail and forwardEmail onCall functions: After fetching email document, check email.provider: if provider === 'gmail': use existing gmail.sendReply / gmail.forwardMessage if provider === 'outlook': use new outlook.sendReply / outlook.forwardMessage if provider === 'imap': throw HttpsError('unimplemented', 'SMTP reply implemented in Phase 6') — placeholder until Task 6.3 No frontend changes required — ReplyForwardComposer.jsx from Task 3.4 is provider-agnostic and calls the same Cloud Functions regardless of provider.

PHASE 6 IMAP / SMTP Weeks 12–13 · 5 Tasks

Phase 6 extends the application to support any email provider that speaks IMAP and SMTP — covering Gmail (via app passwords when OAuth is not preferred), Yahoo Mail, Apple iCloud, Fastmail, self-hosted mail servers, and any corporate Exchange server with IMAP enabled.

Unlike Gmail and Outlook which use OAuth2 flows, IMAP/SMTP uses username and password credentials. These credentials are significantly more sensitive than OAuth tokens — they grant permanent, unrestricted access to the account unless the user changes their password. The encryption and storage of these credentials requires the same AES-256-GCM approach used for OAuth tokens, with an important additional constraint: the credentials must never be returned to the frontend under any circumstances.

Phase 6 also introduces the unified Add Account Wizard — a single UI flow that handles all three provider types (Gmail, Outlook, IMAP) and replaces the ad-hoc connection buttons introduced in earlier phases.

## Task Summary

| Task ID | Week | Task Name |
| --- | --- | --- |
| 6.1 | Week 12 | IMAP Credential Storage + AES-256 Encryption |
| 6.2 | Week 12 | IMAP Fetch (imap + mailparser) |
| 6.3 | Week 13 | SMTP Reply / Forward (nodemailer) |
| 6.4 | Week 13 | IMAP EXPUNGE Delete + UI Warning |
| 6.5 | Week 13 | Add Account Wizard (All 3 Providers) |

Task 6.1 — IMAP Credential Storage + AES-256 Encryption Phase 6 · Week 12 · 6.1

Description

Implement secure storage of IMAP/SMTP credentials — the user provides their email, password, IMAP host/port, and SMTP host/port, which are validated by attempting a real connection before being encrypted and stored.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/index.js | Export connectImap onCall — validate, test, encrypt, store |
| functions/src/auth/encryption.js | AES-256-GCM encrypt/decrypt utilities — centralise encryption used across all providers |
| functions/src/email/imap.js | New IMAP provider module — testConnection(credentials) as first function |
| functions/package.json | Add dependencies: imap@^0.8, mailparser@^3, nodemailer@^6 |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Functions | connectImap onCall — { email, password, imapHost, imapPort, smtpHost, smtpPort, useTLS } |
| IMAP | Connection test using imap npm package — verify credentials before storing |
| Firestore Admin SDK | Write users/{uid}/accounts/{id} with encrypted credentials |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| accounts/{id}.provider | Set to 'imap' |
| accounts/{id}.email | Plaintext — email address |
| accounts/{id}.imapHost | Plaintext — IMAP server hostname |
| accounts/{id}.imapPort | Plaintext — IMAP port (993 for SSL, 143 for STARTTLS) |
| accounts/{id}.smtpHost | Plaintext — SMTP server hostname |
| accounts/{id}.smtpPort | Plaintext — SMTP port (587 for STARTTLS, 465 for SSL) |
| accounts/{id}.encryptedPassword | AES-256-GCM encrypted — NEVER returned to frontend |
| accounts/{id}.useTLS | Boolean — TLS/SSL vs STARTTLS |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js security engineer. Implement secure IMAP credential storage for the AI-Powered Email Sorter. functions/src/auth/encryption.js — centralise all encryption: Export encrypt(plaintext): Generate random 16-byte IV. AES-256-GCM using ENCRYPTION_SECRET (32-char key from env). Return: iv_hex + ':' + ciphertext_hex + ':' + authtag_hex Export decrypt(encryptedString): Parse iv, ciphertext, authtag from string. Decrypt and return plaintext. Throw clear error if decryption fails (wrong key or tampered data). Update all existing uses of encryption in gmail.js, outlook.js to import from here. functions/src/email/imap.js — export testConnection(credentials): credentials: { email, password, imapHost, imapPort, useTLS } Use imap npm package to attempt connection with 10-second timeout. On successful connect: immediately end connection. Return { success: true }. On AUTHENTICATIONFAILED: throw { code: 'auth_failed', message: 'Invalid email or password' } On ECONNREFUSED or ETIMEDOUT: throw { code: 'connection_failed', message: 'Could not reach IMAP server — check host and port' } On certificate error: throw { code: 'tls_error', message: 'TLS certificate error — try disabling TLS verification for self-signed certs' } All other errors: throw { code: 'unknown', message: error.message } functions/src/index.js — export connectImap onCall: 1. verifyToken → uid. 2. Validate all required fields: email, password, imapHost, imapPort, smtpHost, smtpPort. 3. Call testConnection({ email, password, imapHost, imapPort, useTLS }). If it throws: return the error to the client immediately. Do NOT store credentials. 4. Only if testConnection succeeds: Encrypt password using encrypt() from encryption.js. Write to users/{uid}/accounts/{auto-id}: { provider:'imap', email, imapHost, imapPort, smtpHost, smtpPort, useTLS, encryptedPassword, status:'connected', connectedAt:serverTimestamp() } NEVER store plaintext password. NEVER log password. 5. Return { success: true, email }. Security requirement: the password must exist in server memory for the minimum possible time — only during testConnection and encryption. Do not assign it to any persistent variable or include it in any log statement.

Task 6.2 — IMAP Fetch (imap + mailparser) Phase 6 · Week 12 · 6.2

Description

Implement the IMAP email fetch function that connects to the IMAP server, fetches new unread messages from the INBOX, parses the MIME structure, and returns the same normalised message format as the Gmail and Outlook providers.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/email/imap.js | Add fetchMessages(uid, accountDoc, maxResults) — main fetch function |
| functions/src/email/sync.js | Add 'imap' case to provider switch in runSync() |

APIs Used

| API / Service | Usage |
| --- | --- |
| IMAP protocol | SEARCH UNSEEN — find unread message UIDs |
| IMAP protocol | FETCH {uid} (RFC822) — fetch full message for parsing |
| mailparser | simpleParser() — extract from, subject, date, text, html from raw MIME |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| emails/{id}.provider | Set to 'imap' |
| emails/{id}.providerId | IMAP UID as string — used for deduplication and delete |
| emails/{id}.snippet | First 300 chars of parsed plain text body |
| emails/{id}.bodyText | Full plain text body — stored immediately (IMAP fetches full message) |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js email engineer. Implement IMAP message fetching for the AI-Powered Email Sorter using the imap and mailparser npm packages. functions/src/email/imap.js — export fetchMessages(uid, accountDoc, maxResults): Same return shape as gmail.js and outlook.js fetchMessages() — critical for sync. 1. Decrypt password: decrypt(accountDoc.encryptedPassword) from encryption.js. 2. Create IMAP connection: const imap = new Imap({ user: accountDoc.email, password: decryptedPassword, host: accountDoc.imapHost, port: accountDoc.imapPort, tls: accountDoc.useTLS, tlsOptions: { rejectUnauthorized: true }, connTimeout: 15000, authTimeout: 10000 }) 3. Wrap IMAP operations in a Promise for async/await compatibility. imap.once('ready', () => { ... imap.end() }) imap.once('error', reject) 4. On ready: imap.openBox('INBOX', true, (err, box) => { ... }) 5. Search for unseen messages: imap.search(['UNSEEN'], callback) 6. Limit to maxResults most recent UIDs (sort descending, slice). 7. For each UID, fetch RFC822 body. 8. Parse with: const parsed = await simpleParser(rawMessage) 9. Extract from parsed: from: parsed.from.value[0].address fromName: parsed.from.value[0].name subject: parsed.subject receivedAt: parsed.date bodyText: parsed.text?.substring(0, 5000) ¦¦ '' snippet: (parsed.text ¦¦ '').substring(0, 300) 10. Return array of normalised messages with provider:'imap', providerId: uid.toString() Error handling: AUTHENTICATIONFAILED → throw { code: 'auth_error' } ECONNREFUSED, ETIMEDOUT → throw { code: 'network_error' } All errors: log accountDoc.email (not password), include error code. Important: always call imap.end() after fetching, even on error. Use a finally block or ensure end() is called in all code paths. Lingering IMAP connections cause Cloud Function timeouts.

Task 6.3 — SMTP Reply / Forward (nodemailer) Phase 6 · Week 13 · 6.3

Description

Implement reply and forward for IMAP accounts using nodemailer for SMTP, and resolve the 'unimplemented' placeholder set in Task 5.5.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/email/smtp.js | New SMTP module — sendReply() and forwardMessage() via nodemailer |
| functions/src/index.js | Update replyEmail and forwardEmail to handle 'imap' provider case |

APIs Used

| API / Service | Usage |
| --- | --- |
| SMTP protocol | nodemailer createTransport — STARTTLS on port 587, SSL on port 465 |
| nodemailer | transport.sendMail(mailOptions) — RFC 2822 headers for threading |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| accounts/{id}.smtpHost | Read — SMTP server for sending |
| accounts/{id}.smtpPort | Read — 587 (STARTTLS) or 465 (SSL) |
| accounts/{id}.encryptedPassword | Read and decrypted for SMTP authentication |
| Reply threading | In-Reply-To and References headers set to maintain thread in email clients |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js email engineer. Implement SMTP reply and forward using nodemailer for IMAP accounts in the AI-Powered Email Sorter. functions/src/email/smtp.js: Export createTransport(accountDoc): Decrypt password from accountDoc.encryptedPassword. Return nodemailer.createTransport({ host: accountDoc.smtpHost, port: accountDoc.smtpPort, secure: accountDoc.smtpPort === 465, // true for SSL, false for STARTTLS auth: { user: accountDoc.email, pass: decryptedPassword }, connectionTimeout: 15000, greetingTimeout: 10000, }) Export sendReply(accountDoc, { originalMessage, replyText }): const transporter = createTransport(accountDoc) await transporter.verify() // test connection before sending await transporter.sendMail({ from: accountDoc.email, to: originalMessage.from, subject: `Re: ${originalMessage.subject}` (add Re: only if not already present), text: replyText + '\n\n---\n' + originalMessage.snippet, headers: { 'In-Reply-To': originalMessage.messageId ¦¦ '', 'References': originalMessage.messageId ¦¦ '', } }) Return { success: true } Export forwardMessage(accountDoc, { originalMessage, toAddress, noteText }): Validate toAddress format. const transporter = createTransport(accountDoc) await transporter.sendMail({ from: accountDoc.email, to: toAddress, subject: `Fwd: ${originalMessage.subject}`, text: (noteText ? noteText + '\n\n' : '') + '---------- Forwarded message ----------\n' + `From: ${originalMessage.from}\n` + `Subject: ${originalMessage.subject}\n\n` + originalMessage.bodyText?.substring(0, 2000) ¦¦ originalMessage.snippet }) Error handling for both functions: EAUTH: throw { code:'auth_error', message:'SMTP authentication failed' } ECONNREFUSED: throw { code:'connection_failed', message:'SMTP server unreachable' } Other: throw { code:'smtp_error', message: error.message } Always close the transporter after use: transporter.close()

Task 6.4 — IMAP EXPUNGE Delete + UI Warning Phase 6 · Week 13 · 6.4

Description

Implement IMAP email deletion using EXPUNGE — the most destructive delete in the application, as IMAP EXPUNGE is permanent and irrecoverable unlike Gmail Trash or Outlook Deleted Items.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/email/imap.js | Add deleteMessage(accountDoc, imapUid) — marks deleted and expunges |
| functions/src/email/delete.js | Add 'imap' case to provider switch in deleteEmail() |
| frontend/src/components/DeleteConfirmDialog.jsx | Add IMAP-specific warning — stronger language for permanent delete |

APIs Used

| API / Service | Usage |
| --- | --- |
| IMAP protocol | STORE {uid} +FLAGS (\Deleted) — mark for deletion |
| IMAP protocol | EXPUNGE — permanently remove messages flagged as deleted |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| IMAP delete | PERMANENT — no trash folder, no recovery. Document this clearly in UI. |
| users/{uid}/emails/{id} | Deleted from Firestore only after successful EXPUNGE |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js email engineer. Implement permanent IMAP deletion for the AI-Powered Email Sorter. CRITICAL: IMAP EXPUNGE is PERMANENT. There is no Trash. There is no recovery. This is the most destructive operation in the application. The UI warning must be explicit and impossible to dismiss accidentally. functions/src/email/imap.js — export deleteMessage(accountDoc, imapUid): imapUid: the IMAP UID stored in email.providerId 1. Decrypt password, create IMAP connection (same pattern as fetchMessages). 2. Open INBOX in read-write mode: imap.openBox('INBOX', false, callback) Note: false = not readOnly — required for flag operations. 3. Mark message as deleted: imap.addFlags(imapUid, '\\Deleted', callback) 4. Expunge deleted messages: imap.expunge(callback) 5. End IMAP connection. 6. Return { success: true } Error handling: identical to fetchMessages error patterns. Always end IMAP connection in finally block. functions/src/email/delete.js — add 'imap' case: case 'imap': await deleteImapMessage(accountDoc, email.providerId); break; Firestore delete contract identical: delete Firestore doc ONLY after successful expunge. frontend/src/components/DeleteConfirmDialog.jsx — IMAP warning: For IMAP accounts (email.provider === 'imap'), replace existing warning with: Warning box with RED background: '⚠ PERMANENT DELETION' 'IMAP accounts do not have a Trash folder.' 'This email will be PERMANENTLY AND IMMEDIATELY deleted.' 'It cannot be recovered from this application or your email client.' Confirm button text: 'Permanently Delete' (not 'Move to Trash') Type-to-confirm: user must type 'DELETE' before confirm button is enabled. (Same pattern as BulkDeleteConfirmDialog from Task 3.6)

Task 6.5 — Add Account Wizard (All 3 Providers) Phase 6 · Week 13 · 6.5

Description

Build a unified multi-step account connection wizard that consolidates the Gmail OAuth, Microsoft OAuth, and IMAP/SMTP flows into a single coherent UI experience.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/components/AddAccountWizard.jsx | Multi-step wizard — provider selection, credentials, connection test, confirmation |
| frontend/src/components/AddAccountPage.jsx | Updated — shows connected accounts list + 'Add Account' button launching wizard |
| frontend/src/components/AccountListItem.jsx | Connected account row — provider icon, email, last sync, disconnect button |
| frontend/src/components/Sidebar.jsx | Update account section to show real connected accounts |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firebase Functions | connectImap, connectOutlook (existing), connectGmail (Gmail OAuth popup — mirrors Outlook flow) |
| Firestore SDK | onSnapshot on users/{uid}/accounts — real-time account list |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/accounts | Real-time list of all connected accounts — drives sidebar and wizard |
| accounts/{id}.status | 'connected' ¦ 'error' ¦ 'disconnected' |
| accounts/{id}.lastError | Error message if last sync failed |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React engineer. Build the unified Add Account Wizard for the AI-Powered Email Sorter supporting Gmail, Outlook, and IMAP/SMTP accounts. frontend/src/components/AddAccountWizard.jsx: Multi-step modal dialog. Step 1 — Provider Selection: Title: 'Connect an Email Account' Three large cards: Gmail (Google icon, 'Connect with Google OAuth'), Outlook (Microsoft icon, 'Connect with Microsoft OAuth'), IMAP/SMTP ('Works with any email provider') On Gmail click: trigger Google OAuth popup (reuse existing GoogleConnectButton logic) On Outlook click: trigger Microsoft OAuth popup (reuse MicrosoftConnectButton logic) On IMAP click: advance to Step 2 Step 2 — IMAP Credentials (only for IMAP path): Fields: Email address, Password (type=password with show/hide toggle), IMAP Host, IMAP Port (default 993), SMTP Host, SMTP Port (default 587), TLS checkbox (default checked) Common presets button: 'Gmail (App Password)', 'Yahoo', 'iCloud', 'Fastmail' Each preset populates IMAP/SMTP host and port fields automatically. 'Test Connection' button — calls connectImap Cloud Function. Show progress: 'Testing connection...' On success: advance to Step 3. On error: show specific error from Cloud Function (auth_failed, connection_failed etc.) Step 3 — Confirmation: Show: 'Account connected successfully' Show: provider icon + email address For IMAP: show prominent warning: 'Important: Deleting emails from IMAP accounts is PERMANENT.', 'There is no trash or recovery option.' Checkbox: 'I understand that email deletion is permanent' (required for IMAP) Button: 'Done' On wizard close/done: refresh accounts list. Keyboard: Escape closes wizard (with confirmation if mid-flow). frontend/src/components/AccountListItem.jsx: Provider icon (G for Gmail, M for Microsoft, envelope for IMAP) Email address (bold) Status indicator: green dot = connected, red dot = error If status === 'error': show lastError message in amber 'Disconnect' button: removes account document from Firestore. Warn: 'Disconnecting will remove all {n} synced emails from this account.' Require confirmation before proceeding.

PHASE 7 Polish & Production Weeks 14–15 · 6 Tasks

Phase 7 completes the project by addressing everything that makes the application production-ready beyond core functionality: graceful error handling, observable cost and usage metrics, comprehensive quality assurance, and documentation sufficient for the application to be maintained or extended.

Error handling in a real-world application is not an afterthought — it is a first-class feature. Users encounter network failures, expired sessions, rate limits, and unexpected data. Phase 7 ensures every error state has a specific, helpful UI response rather than a generic failure or, worse, a silent blank screen.

The cost monitoring tasks are particularly important for this project because the application incurs real financial cost on every Claude API call. The monitoring dashboard gives the operator visibility into actual monthly spend and provides early warning if usage patterns produce unexpectedly high costs.

## Task Summary

| Task ID | Week | Task Name |
| --- | --- | --- |
| 7.1 | Week 14 | Error State UI + Loading Skeletons |
| 7.2 | Week 14 | Firestore Usage Monitoring |
| 7.3 | Week 14 | Claude API Cost Dashboard |
| 7.4 | Week 15 | Cross-Browser QA (Chrome, Firefox, Safari) |
| 7.5 | Week 15 | README + Developer Setup Documentation |
| 7.6 | Week 15 | Final Deployment + Smoke Test |

Task 7.1 — Error State UI + Loading Skeletons Phase 7 · Week 14 · 7.1

Description

Audit every async operation in the application, ensure each has a defined error state with specific messaging, and implement loading skeleton components for all data-dependent views.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/components/ErrorBoundary.jsx | React error boundary — catches unhandled render errors |
| frontend/src/components/ErrorState.jsx | Reusable error display — icon, message, retry button |
| frontend/src/components/SkeletonLoader.jsx | Animated skeleton components — email list, email detail, folder counts |
| frontend/src/components/ToastNotifications.jsx | Global toast system — success, error, warning, info |
| frontend/src/context/ToastContext.jsx | Toast state provider — addToast, removeToast |
| frontend/src/App.jsx | Wrap in ErrorBoundary |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Error categories | network ¦ auth ¦ rate_limit ¦ not_found ¦ permission ¦ unknown |
| Retry behaviour | Transient errors (network, rate_limit) show Retry button. Auth errors trigger sign-out. |
| Toast lifetime | success: 3s, error: 6s (manual dismiss also available), warning: 5s |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React engineer specialising in production UX. Implement comprehensive error handling and loading states for the AI-Powered Email Sorter. 1. frontend/src/components/ErrorBoundary.jsx: Class component extending React.Component. Catch render errors with componentDidCatch. Render fallback UI: 'Something went wrong' with details in development mode. Include 'Reload Page' button. Wrap entire App in ErrorBoundary in App.jsx. 2. frontend/src/components/ErrorState.jsx: Props: type ('network'¦'auth'¦'rate_limit'¦'not_found'¦'permission'¦'unknown'), message (string), onRetry (function¦null) Renders: appropriate icon, specific user-facing message per type, optional Retry button. Message mapping: network: 'Unable to connect. Check your internet connection.' auth: 'Your session has expired. Please sign in again.' (+ sign-out button) rate_limit: 'Too many requests. Please wait a moment and try again.' not_found: 'This email could not be found. It may have been deleted.' permission: 'You do not have permission to perform this action.' unknown: message prop or 'An unexpected error occurred.' 3. frontend/src/components/SkeletonLoader.jsx: Export multiple components: EmailListSkeleton: 5 rows, each with circle (40px) + 2 lines (full/partial width) EmailDetailSkeleton: header block + 8 lines of varying widths FolderCountSkeleton: small rounded rectangle (replaces count badge) All skeletons use CSS animation: shimmer effect (background: linear-gradient(90deg, #f0f4f8 25%, #d0def0 50%, #f0f4f8 75%) background-size: 200% 100%; animation: shimmer 1.5s infinite) 4. frontend/src/context/ToastContext.jsx + ToastNotifications.jsx: ToastContext: provides addToast({ type, message, duration? }), removeToast(id). ToastNotifications: fixed bottom-right, stack vertically, max 4 visible. Toast types: success (green), error (red), warning (amber), info (blue). Auto-dismiss after duration. Manual close button (×) on each toast. Smooth enter/exit animations. 5. Audit and update all Cloud Function calls in services/functions.js: Wrap all calls in try/catch. Map error codes to ErrorState types: unauthenticated → auth resource-exhausted → rate_limit not-found → not_found permission-denied → permission unavailable, deadline-exceeded → network other → unknown Call addToast with appropriate type and message for every error.

Task 7.2 — Firestore Usage Monitoring Phase 7 · Week 14 · 7.2

Description

Implement Firestore read/write counters in the sync function and provide a usage dashboard that shows daily reads, writes, and how they track against the free-tier allocation.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| functions/src/email/sync.js | Add Firestore operation counters — log reads/writes per sync run |
| functions/src/index.js | Export getUsageStats onCall — reads usage metrics from Firestore |
| frontend/src/components/UsageDashboard.jsx | Usage page showing Firestore and AI cost metrics |
| functions/src/index.js | Export recordUsageMetrics — called at end of each sync run |

APIs Used

| API / Service | Usage |
| --- | --- |
| Firestore Admin SDK | Write to users/{uid}/usage/{YYYY-MM-DD} — daily usage document |
| Firebase Console | Budget alerts already configured in Task 1.3 — reference in dashboard |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/usage/{date}.firestoreReads | Incremented by sync run read count |
| users/{uid}/usage/{date}.firestoreWrites | Incremented by sync run write count |
| users/{uid}/usage/{date}.claudeCalls | Number of Claude API calls made that day |
| users/{uid}/usage/{date}.claudeTokensIn | Total input tokens consumed |
| users/{uid}/usage/{date}.claudeTokensOut | Total output tokens consumed |
| Free tier limits | 50,000 reads/day, 20,000 writes/day, 1 GB storage |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a Node.js and React engineer. Implement usage monitoring for the AI-Powered Email Sorter to track Firestore and Claude API consumption. functions/src/email/sync.js — add usage tracking: After runSync() completes, collect: { firestoreReads: count, firestoreWrites: count, claudeCalls: count, claudeTokensIn: total, claudeTokensOut: total } Call recordUsageMetrics(uid, metrics). To count Firestore operations: maintain a counter object incremented at every Admin SDK read (get, query) and write (set, update, delete) call. This is an approximation — exact counts require Firestore monitoring API. Document the approximation in code comments. To count Claude tokens: the Anthropic SDK response includes: response.usage.input_tokens and response.usage.output_tokens. Accumulate these in classify.js and return with classification result. functions/src/index.js — export recordUsageMetrics (non-callable, internal): Date key: new Date().toISOString().split('T')[0] // 'YYYY-MM-DD' Firestore increment pattern (atomic — safe for concurrent syncs): admin.firestore().doc(`users/${uid}/usage/${dateKey}`).set({ firestoreReads: FieldValue.increment(metrics.firestoreReads), firestoreWrites: FieldValue.increment(metrics.firestoreWrites), claudeCalls: FieldValue.increment(metrics.claudeCalls), claudeTokensIn: FieldValue.increment(metrics.claudeTokensIn), claudeTokensOut: FieldValue.increment(metrics.claudeTokensOut), updatedAt: FieldValue.serverTimestamp() }, { merge: true }) frontend/src/components/UsageDashboard.jsx (route: /usage): Fetch last 30 days of usage documents. Display: 1. Today's stats: reads vs 50,000 limit (progress bar), writes vs 20,000 limit, Claude calls today, estimated today's Claude cost. 2. 30-day chart (recharts LineChart): daily Claude calls line + reads line. 3. Monthly totals: total Claude calls, total tokens, estimated monthly cost. Cost formula: (tokenIn * 0.00000025) + (tokenOut * 0.00000125) USD (Haiku pricing) 4. Free tier status: green if well within limits, amber if >80%, red if >95%. 5. Link to Firebase Console budget alert settings.

Task 7.3 — Claude API Cost Dashboard Phase 7 · Week 14 · 7.3

Description

Build a dedicated cost tracking view for Claude API usage with per-day breakdown, cumulative monthly spend, cost-per-email metric, and projection to end of month.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/components/UsageDashboard.jsx | Extend with dedicated Claude cost section |
| frontend/src/components/CostBreakdownChart.jsx | Bar chart — daily Claude cost over last 30 days |
| functions/src/classifier/classify.js | Return token usage in classification result — feeds into sync metrics |

APIs Used

| API / Service | Usage |
| --- | --- |
| Anthropic API | response.usage.input_tokens and response.usage.output_tokens in every response |
| Recharts | BarChart for daily cost, LineChart for cumulative, custom tooltips |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| users/{uid}/usage/{date}.claudeTokensIn | Input tokens — multiply by $0.00000025 for cost |
| users/{uid}/usage/{date}.claudeTokensOut | Output tokens — multiply by $0.00000125 for cost |
| Cost projection | Average daily cost × remaining days in month = projected additional spend |
| Cost per email | Total month cost / total emails classified = efficiency metric |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a React engineer. Build the Claude API cost dashboard for the AI-Powered Email Sorter application. Haiku pricing (as of 2025): $0.25 per million input tokens, $1.25 per million output tokens. Store pricing as constants — easy to update when pricing changes. frontend/src/components/CostBreakdownChart.jsx: Props: usageData (array of { date, claudeTokensIn, claudeTokensOut }) Recharts BarChart: x-axis = date (short format), y-axis = cost in USD Two bar series: Input cost (blue) + Output cost (teal) stacked Custom tooltip: show date, input tokens, output tokens, total cost Y-axis formatted as '$0.00XX' with enough precision to show sub-cent values Claude cost section in UsageDashboard.jsx: Row 1 — Key metrics (4 stat cards): Today's cost: calculated from today's usage document This month total: sum of all days in current calendar month Cost per email: monthTotal / totalEmailsClassified (from sync metrics) Month projection: avgDailyCost × daysInMonth avgDailyCost = monthTotal / daysElapsed Row 2 — CostBreakdownChart (last 30 days) Row 3 — Model info box: Current model: claude-haiku-4-5 'Switch to claude-sonnet-4-6 if classification accuracy needs improvement.' 'Sonnet costs approximately 20× more per token.' 'Current accuracy threshold for escalation: < 95% on manually reviewed emails.' Row 4 — Budget status: Monthly budget: $5.00 (safe threshold — well above typical $0.23 estimate) Progress bar: currentMonthCost / $5.00 If projection > $5.00: show amber warning 'Projected spend exceeds budget' Link: 'Manage Firebase budget alerts →' (opens Firebase console in new tab)

Task 7.4 — Cross-Browser QA (Chrome, Firefox, Safari) Phase 7 · Week 15 · 7.4

Description

Conduct systematic cross-browser testing across Chrome, Firefox, and Safari, document all defects found, and resolve any layout, JavaScript compatibility, or OAuth popup issues.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| frontend/src/ | Bug fixes only — no new features |
| frontend/src/firebase.js | Verify IndexedDB persistence works in Safari private mode fallback |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Known Safari issues | OAuth popups require user gesture — verify sign-in button triggers directly |
| Known Firefox issues | CSS grid gap support — verify sidebar layout renders correctly |
| IndexedDB | Safari private mode blocks IndexedDB — ensure graceful fallback to memory-only mode |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a QA engineer. Provide a complete cross-browser testing checklist for the AI-Powered Email Sorter application. Test matrix: Chrome (latest), Firefox (latest), Safari (latest on macOS). Test environment: deployed GitHub Pages URL — not localhost. Test suite (execute in this order in each browser): AUTHENTICATION: [ ] Login page renders correctly — no layout overflow [ ] Google sign-in button triggers OAuth popup (not redirect) [ ] OAuth popup opens and completes without being blocked by popup blocker [ ] After sign-in: authenticated shell renders with user email in top bar [ ] Page reload: user remains signed in (persistence working) [ ] Sign out: returns to login page, clears session [ ] Direct URL access to /folder/work before sign-in: redirects to login NAVIGATION: [ ] All 7 folder links in sidebar navigate correctly [ ] Browser back/forward buttons work with React Router [ ] Direct URL /folder/work loads correct folder (SPA routing via 404.html) [ ] /rules route loads rules page [ ] /usage route loads usage dashboard EMAIL SYNC: [ ] Sync button triggers syncEmails Cloud Function [ ] Loading indicator appears during sync [ ] Emails appear in correct folders after sync [ ] Confidence badges render with correct colours [ ] Folder counts update after sync EMAIL ACTIONS (requires at least one synced email): [ ] Click email: full body loads in detail panel [ ] Move email: disappears from current folder, appears in target folder [ ] Delete email: confirmation dialog appears, deletion succeeds [ ] Reply composer: opens, sends, closes SAFARI-SPECIFIC: [ ] OAuth popup: verify sign-in button is direct user gesture (no async delays) [ ] If IndexedDB unavailable (private mode): app still works (no white screen) [ ] Date formatting: verify dates display correctly (Safari strict ISO parsing) Document each failure as: [Browser] [Component] [Steps to reproduce] [Expected] [Actual] Prioritise: P1 = blocks core flow, P2 = visual defect, P3 = minor cosmetic. All P1 defects must be fixed before launch. P2 at developer discretion.

Task 7.5 — README + Developer Setup Documentation Phase 7 · Week 15 · 7.5

Description

Update the README with complete, verified setup instructions, add inline code documentation to all Cloud Functions, and create a CONTRIBUTING.md for future maintainability.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| README.md | Complete rewrite — verified against actual deployed project |
| CONTRIBUTING.md | New — architecture overview, code conventions, adding a new email provider |
| functions/src/ | JSDoc comments on all exported functions |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| Setup time target | A developer unfamiliar with the project should be able to run it locally in under 30 minutes following the README |
| Documentation accuracy | Every command in the README must be executed and verified to work |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a technical writer and senior engineer. Write production-quality documentation for the AI-Powered Email Sorter project. 1. README.md (complete rewrite — replace the Phase 1 stub): Sections in order: - Project description (2-3 sentences, non-technical summary) - Live demo link (https://{username}.github.io/email-sorter) - Screenshots section (placeholder — add actual screenshots) - Feature list: Gmail/Outlook/IMAP sync, AI classification with confidence scores, folder management, user rules, training feedback loop, cost monitoring - Tech stack table (current accurate versions) - Architecture overview: one-paragraph description of data flow from email → sync → classify → Firestore → React UI - Prerequisites: Node.js 20, Firebase CLI, VS Code, Git - Setup steps (numbered, tested, exact commands): 1. Clone, 2. npm install (frontend + functions), 3. Firebase login + use, 4. Configure all .env files, 5. Set Firebase secrets, 6. Start emulators, 7. Start React dev server, 8. Verify app at localhost:3000 - Environment variables reference: table with name, where to find it, and example value - GitHub Secrets reference: table with name, purpose, how to obtain - Deployment: push to main triggers CI/CD — one sentence - Cost profile: table with service, plan, typical monthly cost - Troubleshooting section: 5 most common setup errors with solutions 2. CONTRIBUTING.md: - Architecture overview: directory structure with one-line description per directory - Data flow diagram (ASCII art): User → React → Cloud Function → Gmail/Outlook/IMAP → Anthropic Claude → Firestore → React (real-time) - Code conventions: ES modules in functions, functional components in React, JSDoc on all exports, error codes as string constants - How to add a new email provider: 6-step checklist - How to update the classification prompt: location, testing approach - How to update Firestore security rules: edit, deploy, test in Playground 3. JSDoc for all Cloud Function exports in functions/src/index.js: Each exported function must have: @param {Object} data - request data with all fields documented @param {Object} context - Firebase callable context @returns {Object} - response shape documented @throws {HttpsError} - all possible error codes documented

Task 7.6 — Final Deployment + Smoke Test Phase 7 · Week 15 · 7.6

Description

Execute the final production deployment, run a complete smoke test of all critical paths on the live URL, verify cost monitoring is operational, and confirm the project is complete against the requirements checklist.

Modules Affected or Created

| File / Module | Purpose |
| --- | --- |
| All files | Final deployment — no code changes unless smoke test reveals P1 defect |
| .github/workflows/deploy.yml | Verify final pipeline run succeeds with all jobs green |

APIs Used

| API / Service | Usage |
| --- | --- |
| GitHub Actions | Final pipeline run — verify test, build, functions deploy, pages deploy all pass |
| Firebase Console | Verify Functions deployed, Firestore rules deployed, indexes enabled |
| GitHub Pages | Verify live URL is current build |

Data Created, Read, or Changed

| Data Element | Operation / Notes |
| --- | --- |
| REQ-EMAILSORT-001 checklist | Every requirement traced to implemented feature |
| Smoke test result | Document pass/fail for each critical path |

AI Implementation Prompt

Copy the following prompt in full when directing an AI assistant to implement this task. The prompt is self-contained and includes all context required.

You are a release engineer. Conduct the final production deployment and smoke test for the AI-Powered Email Sorter application. PRE-DEPLOYMENT CHECKLIST: [ ] All Phase 7 tasks complete (7.1–7.5) [ ] No open P1 QA defects from Task 7.4 [ ] All environment variables and GitHub Secrets verified current [ ] Firebase budget alert confirmed active at $0 threshold [ ] Firestore security rules last deployed — verify timestamp in Console [ ] All 6 Firestore indexes status: Enabled (not Building) DEPLOYMENT: git add . && git commit -m 'release: v1.0 — production deployment' git push origin main Monitor GitHub Actions: all 3 steps (test, functions deploy, pages deploy) must be green. If any step fails: do not proceed. Fix the failure, re-push. SMOKE TEST (execute on live URL after successful deployment): Critical path 1 — Authentication: Open live URL > sign in > verify authenticated shell > sign out > verify login page Critical path 2 — Gmail sync: Connect Gmail account > run sync > verify emails appear in folders Critical path 3 — AI classification: Check at least 3 emails > verify confidence badges appear > verify folders are reasonable Critical path 4 — Email actions: Open full email body > move to different folder > verify appears in new folder Critical path 5 — Rules: Create a rule > run sync > verify emails matching rule have blue Rule Match badge Critical path 6 — Cost monitoring: Open /usage > verify today's Claude calls are counted > verify cost is non-zero REQUIREMENTS TRACEABILITY — verify each REQ-EMAILSORT-001 requirement is met: REQ-001: Single user authentication — verified by Critical Path 1 REQ-002: Gmail sync — verified by Critical Path 2 REQ-003: AI classification into 7 folders — verified by Critical Path 3 REQ-004: Confidence scores — verified by Critical Path 3 REQ-005: Email actions (read, move, delete, reply) — verified by Critical Path 4 REQ-006: User rules — verified by Critical Path 5 REQ-007: Training feedback — verified by presence of training signal on folder move REQ-008: On-demand sync — verified by sync button behaviour REQ-009: Cost monitoring — verified by Critical Path 6 REQ-010: Free tier compliance — verified by Firestore and GitHub plan usage PROJECT COMPLETE when: All 6 smoke test critical paths pass. All 10 requirements traced and verified. GitHub Actions pipeline green. No P1 defects open.