## Slide 1
AI-Powered Email Sorter
PROJECT PLAN
Gantt Schedule · PERT Network · Phase Breakdown · Task Register
7
PHASES
40
TASKS
15
WEEKS
Node.js · React · Firebase · Claude
STACK
AI-Powered Email Sorter | Project Plan | PROJ-EMAILSORT-001
PROJ-EMAILSORT-001 | v1.0 | 2026-03-10

## Slide 2
Project Overview
REQ-EMAILSORT-001 v1.1 · SPEC-EMAILSORT-001 v1.0
# | Phase | Weeks | Tasks | Key Deliverable | Priority
1 | Foundation | 1–2 | 7 | Authenticated shell on GitHub Pages | CRITICAL
2 | Gmail + AI | 3–5 | 6 | Gmail syncs & AI sorts email | CRITICAL
3 | Full Email Actions | 6–7 | 6 | Read, delete, reply, categorise | HIGH
4 | Rules Engine | 8–9 | 4 | User rules + AI retraining | HIGH
5 | Outlook Integration | 10–11 | 5 | Microsoft 365 accounts connected | MEDIUM
6 | IMAP / SMTP | 12–13 | 5 | Generic email accounts connected | MEDIUM
7 | Polish & Production | 14–15 | 6 | Error handling, monitoring, docs, QA | LOW
15 Weeks
Total Duration
40 Tasks
Total Tasks
Node.js + Firebase
Backend
Claude Haiku
AI Engine
GitHub Pages
Hosting
AI-Powered Email Sorter | Project Plan | PROJ-EMAILSORT-001
Slide 2 of 6

## Slide 3
Gantt Chart — Project Schedule
Weeks 1–15 · 7 Phases · 40 Tasks
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
W12
W13
W14
W15
Phase 1: Foundation
1.1 GitHub repo + branch strategy
1.2 GitHub Actions CI/CD pipeline
1.3 Firebase project (Blaze + $0 cap)
1.4 Firebase Auth + Google OAuth
1.5 React app skeleton + routing
1.6 Firestore rules + indexes
1.7 Deploy authenticated shell to GH Pages
Phase 2: Gmail + AI Classification
2.1 Gmail API integration (fetch/list)
2.2 Cloud Function: syncEmails
2.3 Claude Haiku classifier
2.4 Confidence scoring + thresholds
2.5 React folder view + email list UI
2.6 Firestore real-time listeners
Phase 3: Full Email Actions
3.1 Read full email body (on demand)
3.2 Recategorise email + training signal
3.3 Delete email (Firestore + Gmail Trash)
3.4 Reply / Forward via Gmail API
3.5 Mark as training example
3.6 Folder bulk actions (delete all, mark read)
Phase 4: Rules Engine
4.1 Rule CRUD UI
4.2 Rule parser (one-time Claude call on save)
4.3 Rule engine in syncEmails (pre-AI)
4.4 Retrain from folder (training context builder)
Phase 5: Outlook Integration
5.1 Microsoft Entra app registration
5.2 Graph API token management (MSAL)
5.3 Outlook message fetch + classification
5.4 Outlook delete (Deleted Items)
5.5 Reply / Forward via Graph API
Phase 6: IMAP / SMTP
6.1 IMAP credential storage + encryption
6.2 IMAP fetch (imap + mailparser)
6.3 SMTP reply/forward (nodemailer)
6.4 IMAP EXPUNGE delete + UI warning
6.5 Add account wizard (all 3 providers)
Phase 7: Polish & Production
7.1 Error state UI + loading skeletons
7.2 Firestore usage monitoring
7.3 Claude API cost dashboard
7.4 Cross-browser QA (Chrome, Firefox, Safari)
7.5 README + developer setup documentation
7.6 Final deployment + smoke test
TODAY
AI-Powered Email Sorter | Project Plan | PROJ-EMAILSORT-001
Slide 3 of 6

## Slide 4
PERT Network — Critical Path Analysis
All paths are critical (linear sequential dependency) · Total duration: 75 working days (15 weeks)
5d
5d
10d
5d
10d
10d
10d
10d
10d
S
START
1A
Repo + Firebase Setup
ES:0
EF:5
LS:0
LF:5
1B
Auth + React Shell
ES:5
EF:10
LS:5
LF:10
2A
Gmail API + syncEmails
ES:10
EF:20
LS:10
LF:20
2B
Classifier + UI
ES:15
EF:25
LS:15
LF:25
3
Full Email Actions
ES:25
EF:35
LS:25
LF:35
4
Rules Engine
ES:35
EF:45
LS:35
LF:45
5
Outlook Integration
ES:45
EF:55
LS:45
LF:55
6
IMAP / SMTP
ES:55
EF:65
LS:55
LF:65
7
Polish + Production
ES:65
EF:75
LS:65
LF:75
E
LAUNCH
Milestone node
Process node
Duration (working days)
Critical path (all paths critical)
ES=Early Start EF=Early Finish LS=Late Start LF=Late Finish Slack=0 for all nodes
AI-Powered Email Sorter | Project Plan | PROJ-EMAILSORT-001
Slide 4 of 6

## Slide 5
Phase Detail — Phases 1, 2, 3, 4
Task breakdown with deliverables and dependencies
Phase 1
Foundation
Wk 1–2
1.1
GitHub repo + branch strategy
W1
1.2
GitHub Actions CI/CD pipeline
W1
1.3
Firebase project (Blaze + $0 cap)
W1
1.4
Firebase Auth + Google OAuth
W1
1.5
React app skeleton + routing
W2
1.6
Firestore rules + indexes
W2
1.7
Deploy authenticated shell to GH Pages
W2
Phase 2
Gmail + AI Classification
Wk 3–5
2.1
Gmail API integration (fetch/list)
W3
2.2
Cloud Function: syncEmails
W3
2.3
Claude Haiku classifier
W4
2.4
Confidence scoring + thresholds
W4
2.5
React folder view + email list UI
W4
2.6
Firestore real-time listeners
W5
Phase 3
Full Email Actions
Wk 6–7
3.1
Read full email body (on demand)
W6
3.2
Recategorise email + training signal
W6
3.3
Delete email (Firestore + Gmail Trash)
W6
3.4
Reply / Forward via Gmail API
W7
3.5
Mark as training example
W7
3.6
Folder bulk actions (delete all, mark read)
W7
Phase 4
Rules Engine
Wk 8–9
4.1
Rule CRUD UI
W8
4.2
Rule parser (one-time Claude call on save)
W8
4.3
Rule engine in syncEmails (pre-AI)
W8
4.4
Retrain from folder (training context builder)
W9
AI-Powered Email Sorter | Project Plan | PROJ-EMAILSORT-001
Slide 5 of 6

## Slide 6
Phase Detail — Phases 5, 6, 7
Task breakdown with deliverables and dependencies
Phase 5
Outlook Integration
Wk 10–11
5.1
Microsoft Entra app registration
W10
5.2
Graph API token management (MSAL)
W10
5.3
Outlook message fetch + classification
W11
5.4
Outlook delete (Deleted Items)
W11
5.5
Reply / Forward via Graph API
W11
Phase 6
IMAP / SMTP
Wk 12–13
6.1
IMAP credential storage + encryption
W12
6.2
IMAP fetch (imap + mailparser)
W12
6.3
SMTP reply/forward (nodemailer)
W13
6.4
IMAP EXPUNGE delete + UI warning
W13
6.5
Add account wizard (all 3 providers)
W13
Phase 7
Polish & Production
Wk 14–15
7.1
Error state UI + loading skeletons
W14
7.2
Firestore usage monitoring
W14
7.3
Claude API cost dashboard
W14
7.4
Cross-browser QA (Chrome, Firefox, Safari)
W15
7.5
README + developer setup documentation
W15
7.6
Final deployment + smoke test
W15
AI-Powered Email Sorter | Project Plan | PROJ-EMAILSORT-001
Slide 6 of 6